## Workplan
Provision of Flood Early Warning to Flood-Vulnerable Communities in the Lower Mekong River Basin, Phase 1: Cambodia and Lao PDR;
WORK PLAN 2005 (Jan-Dec) Draft Version 2.3
Indicates that particular specialist has primary responsibility for completion of the activity.
Indicates participation in and contribution to the outcome of the activity by the specialist.
O U T P U T S / A C T I V I T I E S | I M P L E M E N T A T I O N P E R I O D
| Quarter 1 |  | Quarter 2 | Quarter 3 | Quarter 4 | l
A. Activities for MRCS
AA1. Identification of the potential partners for the project implementation (expansion)
AA2. Procurement of additional project equipments for partners, for Branch Offices. (e.g. Motorcycles, Radios, Computers, Cameras, furniture)
AA3. Installation of flood marks (for new areas)
AA4. Provision of Flood Early Warning to partners
AA5. Villages Flood mapping
AA6. Project management and monitoring
AA7. Provision of required technical services to partners
AA8. Preparation of 2006 Annual Detail Work plan and Budget
AA9. Reporting to OFDA
AA10. Project correspondence
B. Activities (ARC)
Program Administration and Staff Development
Monitor project implementation in flood season and non flood season.
Monitor and Assist the training provided by FOs
Provide technical assistant to CRC EWS staff and CRC branches on a routine basis as and when needed
Coordinate with CRC & ARC managements, and relevant stakeholders as and when needed.
Quarterly and yearly financial and Implementation Reports to MRC.
Quarterly and yearly financial reports to EWS staff for project implementation monitoring for actual expense against budget.
C. Activities (ARC & CRC)
Program Administration and Staff Development
A. Recruit one office assistant and one driver
B. Procure additional office equipment for headquarters/Branch Offices as agreed with MRC
C. Procure bicycles for RCVs in Stung Treng
D. Procure Speaker System, generator, one for each village for all villages
E. Boat with engine one for each village
F. Life jacket, raincoat, T-shirt, Caps
G. CRC & ARC EWS staff will attend Arc View & Ariel Photo
H. CRC EWS staff will attend English class with ACE
I. Monitor project implementation in flood season and non flood season.
J. Monitor and Assist the training provided by FOs
K. Provide technical assistant to CRC branches on a routine basis
L. Coordinate with CRC & ARC managements, and relevant stakeholders as and when needed.
M. CRC & ARC EWS staff will attend Project Planning Monitoring & Evaluation, Project Management, Disaster Risk Communication.
N. Provide travel allowance for one NCDM when he travels with the EWS project. This person will coordinate the project between CRC and NCDM, PCDM, DCDM, CCDM.
O. Quarterly meeting with CRC, ARC, NCDM
P. Six monthly meeting with CRC branches, PCDM, DCDM, CCDM, RCVs, and EWS staff conducting by CRC branches.
Q. Cross visits for EWS Phnom Penh base staff in country and outside country for information sharing, lessons learnt, experiences.
R. Cross visits for RCVs, SBOs, CRC branches, local authority in country for information sharing, lessons learnt, experiences.
S. meeting with RCVs of each branch on a monthly basis conducting by FO for information sharing, issues, and monthly activity schedule development by RCVs.
T. FOs will write quarterly report on EWS project approved by CRC branch director and send to EWS. EWS staff will then compile for all CRC branches and submit to ARC.
U. CRC branch directors, and FOs will manage and monitor the EWS project implementation with technical assistance from EWS staff as and when needed.
V. EWS Accountant will pay salary, and allowance to all CRC branches, SBOs, and RCVs.
W. Workmen compensation insurance for EWS staff (24 coverage including weekends)
X. RCVs and local authority will implement their response activity plans based on outputs 2004 workshop.
Y. EWS staff, NCDM, CRC branches will coordinate and facilitate with NGOs or institutions to implement response activities by RCVs and local authorities.
Z . EWS staff, NCDM, PCDM, DCDM, CCDM, PRC, Foes, SBOs, RCVs develop response activity and annual work plan for 2006 in all four existing provinces, and explore expansion to Tonle Sap basin.
Continued Working in Existing 38 Targeted Villages (2003-2004)
Output 1.1 Flood Referencing Tools, Materials, and Methods
1.1.1 During flood season RCVs will read and report Flood Marker water levels and disseminate MRC EWS warnings and predictions.
1.1.2 Foes will meet regularly with groups of village household to educate Villagers on the EWS Project, and will post educational posters, leaflets throughout the village. With participation and assistance of SBO and RCV)
1.1.3 RCVs will maintain and update information on flood referencing billboards.
1.1.4 During floods, Red Cross Volunteers will collect information on the effects of flood waters at specified times and gauge heights and relay to the CRC branch or sub-branch office.
1.1.5 CRC branch and sub-branch officers will record data and begin to compare the characteristics with known floods of earlier times.
1.1.6 CRC branch, sub branch officers, and RCVs will conduct dissemination during ceremony in a village, a pagoda by using speaker system and lottery.
1.1.7 CRC branch, sub branch officers, and RCVs will provide EWS questionnaires to households to answer, will collect and provide prize for correct answers.
1.1.8 CRC branch officer will regularly confirm data with RCVs and SBO during floods to verify information.
Output 1.2 Early Earning System Guidebooks - Village Manuals for Cambodia
1.2.1 Compile the flood information and provide additional info for MRC mapping
1.2.2 Identify and review existing flood EWS response tools.
1.2.3 Design and Produce EWS response tools for the villages - guidebooks - booklet, posters - relevant for Cambodian audiences/needs using best practices and lesson learnt from the 2003 & 2004 flood referencing. These guidebooks will include general EWS training as well as sections/insertions for village specific information. The village information will be updated yearly.
1.2.4 Translate guidebook into Khmer version
1.2.5 Train CRC branch/sub-branch officers on EWS response tools.
1.2.6 CRC EWS officers will organize workshop for all four CRC branch staff (directors & field officers).
1.2.7 With technical assistance from MRC’s TDS or other sources, CRC will gather information about flood hazard and community at risk and will use the gathered information for developing maps that can be used at the village level as a part of the village EWS Manuals. The maps will show the following:· Extent of one or more historical events along with a range of flood design· Equivalence to a level of difference gauge by using exercise such as high water mark on buildings, and other constructions from the past flood· Location of the most vulnerable groups, individuals, and evacuation route
1.2.8 With assistance from MRC’s TSD and other sources – especially local knowledge sources-, compile flood intelligence records which consist of the known or estimated heights at which phenomena such as the following occur: · Flood water encroach on specific farmlands, residential and business properties, community facilities and other institutions etc· Buildings are flooded over their floorboards· Roads are cut, causing individual house or community to become isolated· Route to safe areas are cut, causing difficulties in evacuating populations.
1.2.9 Using existing Flood EWS guidebooks as reference, design and produce EWS guide book and General EWS educational and promotional materials for ALL villages.
1.2.10 Specific Village Flood response material will be produced for each village included in the guidebooks and distributed to households (leaflets).
Output 1.3 Community Feedback
1.3.1 After the Flood season, Directors,FOs,SBOs, EWSOs staff and RCVs will meet with villagers, and village leaders to determine lessons learned, successes and improvements needed in the project.
1.3.2 Year-end Quarterly report will include recommendations from the villages' feedback meetings.
1.3.3 CRC and NCDM will agree on a phase- in strategy for NCDM for dissemination of MRC warnings and predications. Once NCDM takes on this role, the feedback from the community will be addressed to NCDM - both field and HQ. Until that time, the feedback will be addressed to CRC - field and NHQ.
ARC management
Team Leader/Flood Management Specialist
Hydrologist
GIS/Mapping Specialist
Assistant Hydrologist
Disaster management Specialist (Team Leader)
Community-based Disaster Management Specialist
Partner(s)
CBDM Training Specialist
Field personnel (Volunteers)
Flood Management Specialist (individual consultant) * Optional
E X P E R T S
MRSC

## Experts
v2.3
Expertise Required for the Project in 2005
| POSITIONS | Months | [11 empty] | MRC Expert | Partner | TOTAL
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | person.month | person.month | person.month
| Team Leader/Flood Management Specialist | [12 empty] | 12 |  | 12
| GIS/Mapping Specialist | [12 empty] | 5 |  | 5
| Hydrologist | [12 empty] | 4 |  | 4
| Assistant Hydrologist | [12 empty] | 6 |  | 6
| Flood Management Specialist (individual consultant) * | [12 empty] | 3 |  | 3
| Secretary | [12 empty] | 12 |  | 12
| Driver | [12 empty] | 12 |  | 12
| Disaster Management Specialist | [13 empty] | 36 | 36
| Disaster Management Support | [13 empty] | 30 | 30
| Community-based Disaster Management Specialists) | [13 empty] | 96 | 96
| CBDM Training Specialist | [13 empty] | 48 | 48
ARC Management
| FEW Programme Manager | [13 empty] | 12 | 12
| Head of Delegation | [13 empty] | 5 | 5
Regional Financial Analyst
| Other General AmCross In-country Support Staff | [13 empty] | 5 | 5
MRCS Experts/staff
Partners

## Breakdowns Budget
Refer ence # | Work plan Activity | COST ESTIMATE/BREAKDOWNS
EWS-05 v2.3
|  | Personnel | No. of | No. of | Monthly | Estimated | Required from |  | CRC | ARC | MRC | Total | Acct Code
|  |  | Day.Time | Person-Months | Rate | Amount | Project | Amount
[5 empty] | ($) | ($) | % | ($)
MRCS
MR-1 |  | Team Leader/Flood Management Specialist |  | \ | 2700 | #VALUE! | 100% | #VALUE! |  |  | #VALUE!
MR-2 |  | GIS/Mapping Specialist |  | 5 | 2500 | 12500 | 0% | 0 |  |  | 0
MR-3 |  | Hydrologist |  | 4 | 2500 | 10000 | 0% | 0 |  |  | 0
MR-4 |  | Assistant Hydrologist |  | 6 | 1000 | 6000 | 0% | 0 |  |  | 0
MR-5 |  | Flood Management Specialist (individual consultant) * |  | 3 | 15000 | 45000 | 10% | 4500 |  |  | 4500
MR-6 |  | Secretary |  | 12 | 500 | 6000 | 100% | 6000 |  |  | 6000
MR-7 |  | Driver |  | 12 | 220 | 2640 | 100% | 2640 |  |  | 2640 | #VALUE!
ARC & CRC
AR-1 |  | Disaster Management Specialist (CRC-EWS Officer) |  | 12 | 330 | 3960 | 100% | 3960 | 3960
AR-2 |  | Disaster Management Specialist (CRC-EWS Assistant) |  | 11 | 315 | 3465 | 100% | 3465 | 3465
AR-3 |  | Disaster Management Support (Accountant) |  | 12 | 315 | 3780 | 100% | 3780 | 3780
AR-4 |  | Office Assistant |  | 11 | 200 | 2200 | 100% | 2200 | 2200
AR-5 |  | EWS-Driver |  | 6 | 200 | 1200 | 100% | 1200 |  | 1200
AR-6 |  | Community-based Disaster Management Specialist(s)- FOs |  | 48 | 250 | 12000 | 100% | 12000 | 12000
AR-7 |  | Branch Director (BDs) |  | 48 | 160 | 7680 | 50% | 3840 | 3840
AR-8 |  | ARC Management
AR-9 |  | EWS Program Manager |  | 12 | 639.0417 | 7668.5 | 100% | 7668.5 |  | 7668.5
AR-10 |  | Regional Manager |  | 12 | 8514.5833 | 102175 | 10% | 10217.5 |  | 10217.5
AR-11 |  | Regional Financial Analyst |  | 12 | 7537.5 | 90450 | 5% | 4522.5 |  | 4522.5
AR-12 |  | Head of Delegation |  | 12 | 11489.75 | 137877 | 41.67% | 57448.75 |  | 57448.75
AR-13 |  | ARC Support Staff |  | 12 | 2051 | 24612 | 42% | 10337.04 |  | 10337.04
AR-14 | [11 empty] | 120639.29 |  | 29245 | 90194.29
AR-15 |  | Travel | [11 empty] | 24.49% | 75.51%
AR-16 |  | Allowance
AR-17 | F | Allowance for EWS Project
AR-18 |  | CRC-EWS staff and NCDM |  | 30 | 196 | 5880 | 100% | 5880 | 5880
AR-19 |  | EWS Driver |  | 6 | 180 | 1080 | 100% | 1080 | 1080
AR-20 |  | ARC-EWS staff |  | 10 | 211 | 2110 | 100% | 2110 |  | 2110
AR-21 |  | CRC branch director
AR-22 |  | Kandal |  | 12 | 160.5 | 1926 | 100% | 1926 | 1926
AR-23 |  | Prey Veng |  | 12 | 152.25 | 1827 | 100% | 1827 | 1827
AR-24 |  | Kratie |  | 12 | 123.75 | 1485 | 100% | 1485 | 1485
AR-25 |  | Stung Treng |  | 12 | 151.5 | 1818 | 100% | 1818 | 1818
AR-26 |  | Provincial Field Officer (FOs)
AR-27 |  | Kandal |  | 12 | 89.25 | 1071 | 100% | 1071 | 1071
AR-28 |  | Prey Veng |  | 12 | 70.5 | 846 | 100% | 846 | 846
AR-29 |  | Kratie |  | 12 | 52.5 | 630 | 100% | 630 | 630
AR-30 |  | Stung Treng |  | 12 | 106.5 | 1278 | 100% | 1278 | 1278
AR-31
AR-32 |  | Allowance for SBOs in Non Flood Season |  | 24 | 29.5 | 708 | 100% | 708 | 708
AR-33 |  | Allowance for SBOs in Flood Season |  | 24 | 64.5 | 1548 | 100% | 1548 | 1548
AR-34 |  | Allowance for RCVs in Non Flood Season |  | 228 | 36 | 8208 | 100% | 8208 | 8208
AR-35 |  | Allowance for RCVs in Flood Season |  | 228 | 71 | 16188 | 100% | 16188 | 16188
AR-36 |  | Travel
AR-37 |  | Cross project visits-travel in country (EWS staff,CRC branch, RCVs...) |  | 4 | 190 | 760 | 100% | 760 | 760
AR-38 |  | Per diem (3ds), Accommodation(2ns) and local travel |  | 41 | 52 | 2132 | 100% | 2132 | 2132
AR-39 |  | Cross visit- travel cost outside country |  | 4 | 50 | 200 | 100% | 200 | 150 | 50
AR-40 | Q & R | Per diem (3days) and Accommodation (2nights) |  | 4 | 133 | 532 | 100% | 532 | 532
AR-41 |  | RCV Six month meeting snack for refreshment | 2 | 42 | 2 | 168 | 100% | 168 | 168
AR-42 |  | Six monthly meetings at CRC branch (DCDM, CCDM) travel | 4 | 18 | 4 | 288 | 100% | 288 | 288
AR-43 |  | Per diem, Accom and snack for refreshment | 2 | 18 | 27 | 972 | 100% | 972 | 972
AR-44 |  | Six monthly meetings at CRC branch (PCDM) | 2 | 4 | 9 | 72 | 100% | 72 | 72
AR-45 |  | Six monthly meetings at CRC branch (EWS staff) | 2 | 4 | 1 | 8 | 100% | 8 | 8
AR-46
AR-47 |  | Work Plan 2006 Dev. & Response Act. (RCVs & SBOs) | 2 | 42 | 4 | 336 | 100% | 336 | 336
AR-48 |  | Work Plan 2006 Dev. & Response Act. (DCDM, CCDM) | 2 | 18 | 4 | 144 | 100% | 144 | 144
AR-49 |  | Work Plan 2006 Dev. & Response Act. (DCDM, CCDM) |  | 18 | 45.5 | 819 | 100% | 819 | 819
AR-50 |  | Work Plan 2006 Dev. & Response Act. (PCDM) | 2 | 4 | 8 | 64 | 100% | 64 | 64
AR-51 |  | Work Plan 2006 Dev. & Response Act. (EWS staff) | 4 | 4 | 2 | 32 | 100% | 32 | 32
AR-52
AR-53 |  | Feedback survey travel cost for ST | 1 |  | 15 | 15 | 100% | 15 | 15
AR-54 |  | Feedback survey travel cost for KD,PV,KT | 9 | 4 | 5 | 180 | 100% | 180 | 180
AR-55 |  | Feedback survey in PV & ST | 1 | 4 | 80 | 320 | 100% | 320 | 320
AR-56 |  | Feedback survey in KD & KT | 1 | 4 | 62 | 248 | 100% | 248 | 248
AR-57 |  | New site project selection | 1 | 4 | 170 | 680 | 100% | 680 | 680
AR-58
AR-59 |  | Field visits (Sub-recipient Monitoring) | 1 | 12 | 90 | 1080 | 100% | 1080 |  | 1080
AR-60 |  | Annual Finance Administration Workshop |  | 1 | 2500 | 2500 | 50% | 1250 |  | 1250
AR-61 |  | NHQ Monitoring visit |  |  |  | 6632 | 100% | 6632 |  | 6632
AR-62 |  | Flood forum in Lao |  | 4 | 403 | 1612 | 100% | 1612 | 1209 | 403
AR-63
AR-64 | [11 empty] | 65147
AR-65 |  | Training/meeting/feedback survey
AR-66 |  | External Training EWS |  | 3 | 250 | 750 | 100% | 750 | 500 | 250
AR-67 |  | English lessons (ACE) | 2 | 3 | 150 | 900 | 100% | 900 | 900
AR-68 |  | EWS staff attend training course (ADPC)- MRC will offer or work on with no cost |  |  |  | 0 |  | 0 | 0
AR-69 |  | Usaid Rules &Reg for 1 CRC Staff |  | 1 | 1150 | 1150 | 100% | 1150 | 1150
AR-70 |  | Usaid Rules &Reg for 1 ARC Staff |  | 1 | 1150 | 1150 | 50% | 575 |  | 575
AR-71
AR-72 | [11 empty] | 3375
AR-73 |  | Office supplies
AR-74 |  | Supplies for EWS |  | 12 | 100 | 1200 | 100% | 1200 | 1200
AR-75 |  | Supplies at ARC |  | 12 | 120 | 1440 | 42% | 604.8 |  | 604.8
AR-76 |  | Telephone
AR-77 |  | Telephone fees- Landline(IDD) at EWS |  | 12 | 130 | 1560 | 100% | 1560 | 1560
AR-78 |  | Telephone fees at ARC |  | 12 | 450 | 5400 | 42% | 2268 |  | 2268
AR-79 |  | Internet fees (EWS office) |  | 12 | 120 | 1440 | 100% | 1440 | 1440
AR-80 |  | Internet fee at ARC |  | 12 | 110 | 1320 | 42% | 554.4 |  | 554.4
AR-81
AR-82 |  | Office Supplies for MRCS |  | 12 | 250 |  | 100% | 3000 |  |  | 3000 | 10627.2
AR-83
AR-84
AR-85 |  | Equipments/Office equipment
AR-86 |  | Computers& printers (2 desktops for EWS staff, 2 for ST. & KT ) |  | 4 | 1000 | 4000 | 100% | 4000 |  |  | 4000
AR-87 |  | Photocopy Machine |  | 1 | 1100 | 1100 | 100% | 1100 |  |  | 1100
AR-88 |  | Digital Camera |  | 1 | 400 | 400 | 100% | 400 |  |  | 400
AR-89 |  | Boat |  | 38 | 300 | 11400 | 100% | 11400 |  |  | 11400
AR-90 |  | Bicycle |  | 18 | 60 | 1080 | 100% | 1080 |  |  | 1080
AR-91 |  | Loud Speakers |  | 38 | 100 | 3800 | 100% | 3800 |  |  | 3800
AR-92 |  | File cabinet |  | 2 | 80 | 160 | 100% | 160 | 160
AR-93 |  | Writing table |  | 2 | 90 | 180 | 100% | 180 | 180
AR-94 |  | Computer desk |  | 2 | 60 | 120 | 100% | 120 | 120
AR-95 |  | Office chair |  | 3 | 50 | 150 | 100% | 150 | 150
AR-96 |  | Chairs for meeting |  | 15 | 30 | 450 | 100% | 450 | 450
AR-97 |  | Water cooler |  | 1 | 150 | 150 | 100% | 150 | 150
AR-98 |  | Air conditioners |  | 3 | 250 | 750 | 100% | 750 | 750
AR-99 |  | Scanner for ARC |  | 1 | 400 | 400 | 42% | 168 |  | 168
AR-100 |  | Scanner for CRC-EWS |  | 1 | 400 | 400 | 100% | 400 | 400
AR-101
AR-102 |  | Equipment Maintenance
AR-103 |  | Flood marks maintenance |  | 5 | 200 | 1000 | 100% | 1000 |  |  | 1000
AR-104 |  | Billboards maintenance |  | 38 | 10 | 380 | 100% | 380 |  |  | 380
AR-105 |  | Office equipment maintenance (comp, printer,..) |  | 12 | 50 | 600 | 100% | 600 | 600
AR-106 |  | Maintenance cost & Fuel for ARC vehicles |  | 12 | 250 | 3000 | 42% | 1260 |  | 1260
AR-107 |  | Maintenance cost & Fuel for EWS Vehicle |  | 12 | 150 | 1800 | 100% | 1800 | 1800
AR-108 |  | Vehicle insurance |  |  |  | 2857 | 42% | 1199.94 |  | 1199.94
AR-109 |  | Maintenance cost & Fuel for motorcycle |  | 12 | 10 | 120 | 100% | 120 | 120
AR-110 |  | Office Rent and Utilities EWS office |  | 12 | 550 | 6600 | 100% | 6600 | 6600
AR-111 |  | Office Rent and Utilities ARC Phnom Penh |  | 12 | 1500 | 18000 | 42% | 7560 |  | 7560
AR-112 |  | Workmen compensation (24 hrs coverage)-CRC-EWS |  | 5 | 55 | 275 | 100% | 275 | 275
AR-113 |  | Workmen compensation (24 hrs coverage)-ARC |  | 8 | 55 | 440 | 42% | 184.8 |  | 184.8
AR-114 |  | Medical expenses for ARC |  | 8 | 100 | 800 | 42% | 336 |  | 336
AR-115 |  | Consultant Fee for feedback report |  | 2 | 200 | 400 | 100% | 400 |  | 400
AR-116 |  | Survey Data Entry for feedback forms |  | 400 | 1.5 | 600 | 100% | 600 |  | 600
AR-117 |  | Security guards for ARC (Office & HOD's house) |  | 12 | 650 | 7800 | 42% | 3276 |  | 3276
AR-118
AR-119 |  | ARC OFFERS ONE VEHICLE (4 WHEEL DRIVE JEEP CHEROKEE) TO BE BASED IN EWS OFFICE
AR-120 | [11 empty] | 49899.74
AR-121 |  | IEC Material and Village Guidebook
AR-122
AR-123 |  | Village guidebook |  | 100 | 15 | 1500 | 100% | 1500 | 1500
AR-124 |  | Leaflets one per household |  | 11350 | 0.048 | 544.8 | 100% | 544.8 | 544.8
AR-125 |  | Posters five per village |  | 250 | 0.43 | 107.5 | 100% | 107.5 | 107.5
AR-126 |  | Identify and review existing flood EWS response tools |  | 2 | 52 | 104 | 100% | 104 | 104
AR-127 |  | Life Jacket |  | 100 | 10 | 1000 | 100% | 1000 |  | 1000
AR-128 |  | T-shirt and cap |  | 200 | 4 | 800 | 100% | 800 |  | 800
AR-129 |  | Raincoat |  | 100 | 4 | 400 | 100% | 400 |  | 400
AR-130 |  | Prize gift (soap 1250 pieces) |  | 2 | 130 | 260 | 100% | 260 |  | 260
AR-131
AR-132
AR-133 |  | Feedback Survey/Forms
AR-134
AR-135 |  | Feedback survey form copies |  | 425 | 0.13 | 55.25 | 100% | 55.25 | 55.25 |  |  | 4771.55
AR-136
AR-137
AR-138 |  | TOTAL | [5 empty] | #VALUE! | 103683.55 | 124616.23 | #VALUE! | #VALUE!
[8 empty] | #VALUE! |  |  |  | #VALUE!
[12 empty] | 228299.78 | ARC&CRC
[12 empty] | #VALUE! | MRC
|  |  |  | PERSONNEL |  |  |  |  | 29245 | 91394.29 | #VALUE!
|  |  |  | TRAVEL |  |  |  |  | 53622 | 11525
|  |  |  | Training/meeting/feedback survey |  |  |  |  | 2550 | 825
|  |  |  | Supplies |  |  |  |  | 4475 | 8224 | 3000
|  |  |  | Equipment |  |  |  |  | 11480 | 10187.94 | 23160
|  |  |  | Materials |  |  |  |  | 2311.55 | 2460
[9 empty] | 103683.55 | 124616.23 | #VALUE! | #VALUE!
#VALUE!
[9 empty] | 0 | 0 | #VALUE! | Dif