## 2007 workplan
6 January 2007 version
Provision of Flood Early Warning to Flood-Vulnerable Communities in the Lower Mekong River Basin
Phase 1: Cambodia
WORK PLAN 2007 (January - March)
Flood Season (June - November)
Non-flood Season (December - May)
| Outputs / Activities | Implementation Period (Months) |  |  | Responsible person(s) and/or organization
A. | Activities for MRC | Jan | Feb | March
AA1. | Project management and monitoring |  |  |  | MRC, CRC HQ, CRC BD, CRC FO, AMCROSS, NCDM
AA2. | Project final evaluation by external consultant (includes endline survey) |  |  |  | MRC, CRC HQ, CRC BD, CRC FO, AMCROSS, NCDM
AA3. | Handover of project equipment to local authorities |  |  |  | MRC, AmCross, CRC, NCDM, CNMC
AA4. | Final audit by external contractor | Date to be identified |  |  | MRC
AA5. | Report to OFDA |  |  |  | MRC
B. | Activities for AmCross | Jan | Feb | March
A. | Monitor project implementation and financial expenditure in non flood season. |  |  |  | CRC HQ, AMCROSS, NCDM
B. | Monitor and assist basic training provided by FOs to newly established 38 PSC village groups based on existing EWS training curriculum. Two one-day trainings will be provided to each of the 38 PSC village groups at the community level. (The training curriculum was developed in 2006 and was used to train RCVs. The trainings will be given to the PSC groups in the subjectsindicated in activity 1.5.1) |  |  |  | CRC BD, CRC FO, CRC SBO
C. | Compile information from target CRC branches into a quarterly report and submit to AmCross, CRC HQ and NCDM. |  |  |  | CRC HQ, NCDM
D. | Submit quarterly reports to Amcross NHQ and annual financial reports to MRC. |  |  |  | AMCROSS
E. | Review and create monthly development plans, discuss relevant issues, and share experiences between PSC and CCDM. |  |  |  | CRC BD, CRC FO, CRC SBO
Output 1.1 | Flood Referencing Tools and Methods | Jan | Feb | March
1.1.1 | Continue to conduct flood information dissemination in schools before flood season when schools are open. (Red Cross volunteers will visit schools and present basic project messages to the teachers and students) |  |  |  | CRC FO, CRC SBO, PSC, CCDM
Output 1.2 | Early Warning System Communication Materials | Jan | Feb | March
1.2.1 | Develop Flood Early Warning System project best practices and submit to CRC HQ and NCDM as well as make it avaiable to all concerned agencies at all levels. |  |  |  | CRC HQ, CRC BD, CRC FO, CRC SBO, AMCROSS, NCDM
1.2.2 | Continued project dissemination through the CRC Website and TV station. | Project information is disseminated throughout the project life. |  |  | CRC HQ, AMCROSS
1.2.3 | Monitor that PSCs maintain and repair billboards and village flood markers during the dry seasons with contribution by villagers. |  |  |  | CRC FO, CRC SBO
Output 1.3 | Village Participation and Contribution | Jan | Feb | March
1.3.1 | Strengthen PSC structure as to the PSC TOR. (Note below) |  |  |  | CRC, AmCross, NCDM
1.3.2 | Assist PSC to develop funding management system in 38 villages. |  |  |  | CRC, AmCross, NCDM
1.3.3 | Monitor that community funds are collected with a transparent and fund reporting system. |  |  |  | CRC, AmCross, NCDM
Output 1. 4 | Handover | Jan | Feb | March
1.4.1 | Verify inventory in Phnom Penh and provincial project offices. |  |  |  | AmCross, CRC
1.4.2 | Consult with CRC HQ, NCDM HQ, and Cambodian National Mekong Committee (CNMC) at national level about handover of the EWS project to communities (inventory distribution plan will be developed) |  |  |  | MRC, CRC, AMCROSS
1.4.3 | Organize meeting to discuss handover plans to NCDM in each province with PCDM, DCDM, CCDM, PSCs, and stakeholders. |  |  |  | CRC HQ, AMCROSS, NCDM, CRC FO
1.4.4 | Present Final Evaluation report |  |  |  | Final Evaluation Consultant
Output 1. 5 | Capacity Building | Jan | Feb | March
1.5.1 | Provide basic training by FOs to newly established PSC members based on existing EWS training curriculum. Training topics to be provided: (First one-day training: Disaster Management, Flood Early Warning, Flood Preparedness, and Interpretation of flood markers and billboards) and (Second one-day training: Community Activity Plans, Basic Communication Skills, Basic Facilitaition, and Fund Raising). The two one-day trainings will be provided to PSC members at the community levels. |  |  |  | CRC BD, CRC FO, DCDM
1.3.1 Note: The PSC groups will receive visits from the Phnom Penh based staff during January and February, which will emphasize the roles and responsibilities of the PSC group. The PSC group is the key component to ensure the continuation of project activities. Control of funds collected by the community to maintain the flood early warning system and an effective flow of information to ensure that the community members receive the adequate information to prepare for a significant rise in waters are two of the key messages that will be enforced during the monitoring trips from headquarter staff. The two one-day trainings planned in January will also provide a means to further emphasize the key messages.
AmCross | American National Red Cross
BDs | Branch Director
CNMC | Cambodia National Mekong Committee
CRC | Cambodian Red Cross
CCDM | Commune Committee for Disaster Management
DCDM | District Committee for Disaster Management
DHRW | Department of Hydrology and River Works
EWS | Early Warning System
FAS | Financial and Administration Section of MRC Secretariat
Field Officers
IEC | Information Education and Communication
MRC | Mekong River Commission
MRCS | Mekong River Commission Secretariat
NCDM | National Committee for Disaster Management
PCDM | Provincial Committee for Disaster Management
PRC | Provincial Red Cross
PSC | Project Support Committee
RCV | Red Cross Volunteer
SBOs | Sub-Branch Officers

## 2007 budget
6 January 2007 version
Provision of Flood Early Warning to Flood-Vulnerable Communities in the Lower Mekong River Basin, Phase I: Cambodia
CRC BUDGET PLAN 2007 (January - March)
No. |  | Quantity | Unit | Quantity | Unit | Unit Cost | TOTAL amount | Required from project | BUDGETED amount | CRC
[6 empty] | ($) | ($) | (%) | ($)
PERSONEL
| CRC | [5 empty] | 9261 |  | 8205 | 8205
1 | CRC Disaster Management Specialist Officer | 1 | person | 3 | months | 364 | 1092 | 100% | 1092 | 1092
2 | CRC Disaster Management Specialist Assistant | 1 | person | 3 | months | 347 | 1041 | 100% | 1041 | 1041
3 | CRC Disaster Management Support Accountant | 1 | person | 3 | months | 347 | 1041 | 100% | 1041 | 1041
4 | CRC Office Assistant | 1 | person | 3 | months | 221 | 663 | 100% | 663 | 663
5 | CRC Community-based Disaster Management Specialists (Field Officers) | 4 | person | 3 | months | 276 | 3312 | 100% | 3312 | 3312
6 | CRC Branch Directors | 4 | person | 3 | months | 176 | 2112 | 50% | 1056 | 1056
TRAVEL
| CRC | [5 empty] | 9391.25 |  | 9391.25 | 9391.25
Phnom Penh based Project staff
7 | CRC Project Officer or CRC Project Assistant | 1 | person | 2 | months | 186 | 372 | 100% | 372 | 372
8 | CRC Accountant | 1 | person | 3 | months | 144 | 432 | 100% | 432 | 432
9 | CRC Disaster Management Director | 1 | person | 1 | time | 81 | 81 | 100% | 81 | 81
| CRC branch directors (flood and non-flood) | [5 empty] | 0
10 | Kandal | 1 | person | 3 | months | 30 | 90 | 100% | 90 | 90
11 | Prey Veng | 1 | person | 3 | months | 25 | 75 | 100% | 75 | 75
12 | Kratie | 1 | person | 3 | months | 10 | 30 | 100% | 30 | 30
13 | Stung Treng | 1 | person | 3 | months | 25 | 75 | 100% | 75 | 75
| Provincial Field Officer (flood and non-flood) | [5 empty] | 0
14 | Kandal | 1 | person | 3 | months | 46.6 | 139.8 | 100% | 139.8 | 139.8
15 | Prey Veng | 1 | person | 3 | months | 32 | 96 | 100% | 96 | 96
16 | Kratie | 1 | person | 3 | months | 13.5 | 40.5 | 100% | 40.5 | 40.5
17 | Stung Treng | 1 | person | 3 | months | 32 | 96 | 100% | 96 | 96
| Sub Branch Officers (SBOs) | [5 empty] | 0
18 | SBOs in Non Flood Season | 5 | persons | 3 | months | 21 | 315 | 100% | 315 | 315
| Red Cross Volunteers (RCVs) two per village | [5 empty] | 0
19 | RCVs in Non Flood Season | 76 | RCVs | 3 | months | 12 | 2736 | 100% | 2736 | 2736
20 | RCVs for Endline Survey | 76 | RCVs | 2 | days | 8.5 | 1292 | 100% | 1292 | 1292
| Provincial, District and Commune Committee for Disaster Management | [5 empty] | 0
21 | PCDM - Kandal | 1 | persons | 3 | months | 29.7 | 89.1 | 100% | 89.1 | 89.1
22 | PCDM - Prey Veng | 1 | persons | 3 | months | 22.2 | 66.6 | 100% | 66.6 | 66.6
23 | PCDM - Kratie | 1 | persons | 3 | months | 15.45 | 46.35 | 100% | 46.35 | 46.35
24 | PCDM - Stung Treng | 1 | persons | 3 | months | 35.7 | 107.1 | 100% | 107.1 | 107.1
25 | DCDMs | 5 | persons | 3 | months | 15.45 | 231.75 | 100% | 231.75 | 231.75
26 | CCDMs | 13 | persons | 3 | months | 15.45 | 602.55 | 100% | 602.55 | 602.55
27 | Kandal Handover meeting | 39 | Persons | 1 | time | 9.75 | 380.25 | 100% | 380.25 | 380.25
28 | Prey Veng Handover meeting | 29 | Persons | 1 | time | 7.75 | 224.75 | 100% | 224.75 | 224.75
29 | Kratie Handover meeting | 12 | Persons | 1 | time | 6.75 | 81 | 100% | 81 | 81
30 | Stung Treng Handover meeting | 24 | Persons | 1 | time | 9.75 | 234 | 100% | 234 | 234
31 | Handover meeting with Phnom Penh based Stakeholders | 25 | Persons | 1 | time | 20.5 | 512.5 | 100% | 512.5 | 512.5
32 | PSC Training | 126 | persons | 2 | time | 3.75 | 945 | 100% | 945 | 945
SUPPLIES
| CRC | [5 empty] | 1572 |  | 1572 | 1572
33 | CRC Office Supplies and other expendable supplies | 1 | office | 3 | months | 120 | 360 | 100% | 360 | 360
34 | Certicate for PSC members and RCVs | 202 | Item | 1 | time | 1 | 202 | 100% | 202 | 202
35 | Training Supplies for PSC members | 202 | Item | 1 | time | 1 | 202 | 100% | 202 | 202
36 | Supply bags for PSC members and RCVs | 202 | Item | 1 | time | 4 | 808 | 100% | 808 | 808
EQUIPMENT/OFFICE MAINTENANCE
| CRC | [5 empty] | 119.25 |  | 119.25 | 119.25
37 | CRC Office equipment maintenance (comp, printer,..) | 1 | office | 3 | months | 30 | 90 | 100% | 90 | 90
38 | Motorcycle insurance for project motorbikes | 3 | motorbikes | 0.25 | year | 39 | 29.25 | 100% | 29.25 | 29.25
ADMINISTRATION
| CRC | [5 empty] | 2295 |  | 2295 | 2295
39 | CRC Office Rent and Utilities | 1 | office | 3 | months | 430 | 1290 | 100% | 1290 | 1290
40 | CRC Telephone fees - Landline (IDD) | 1 | time | 3 | months | 120 | 360 | 100% | 360 | 360
41 | CRC office internet fee | 1 | time | 3 | months | 90 | 270 | 100% | 270 | 270
42 | CRC Phone Card for project staff | 1 | year | 3 | months | 65 | 195 | 100% | 195 | 195
43 | CRC Phone Card for four CRC branches - Non flood season | 4 | branches | 3 | months | 15 | 180 | 100% | 180 | 180
CONTRACTUAL
| Final Evaluation | [5 empty] | 364 |  | 364 | 364
44 | CRC Project Officer costs for final evaluation | 1 | person | 14 | days | 26 | 364 | 100% | 364 | 364
| TOTAL | [8 empty] | 21946.5