## MRC project workplan 2006
version: January 10, 2006
Provision of Flood Early Warning to Flood-Vulnerable Communities in the Lower Mekong River Basin
Phase 1: Cambodia and Lao PDR
WORK PLAN 2006 (January - December)
Flood Season (June - November)
Non-flood Season (December - May)
| O U T P U T S / A C T I V I T I E S | I M P L E M E N T A T I O N P E R I O D
|  | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  |  | Responsible person(s) and/or organization
A. | Activities for MRCS | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
AA1. | Procure additional project equipments for partners | [12 empty] | MRC | bar: Quarter 1 Jan to Quarter 1 Mar
AA2. | Provide Flood Early Warning forecasts to partners | [12 empty] | MRC, CRC HQ, CRC FO, RCVs | bar: Quarter 3 Jul to Quarter 4 Oct
AA3. | Project management and monitoring | [12 empty] | MRC, CRC HQ, CRC BD, CRC FO, AMCROSS, NCDM
AA4. | Provide required technical services to partners | [12 empty] | MRC
AA5. | Prepare of 2007 Annual Detail Work plan and Budget | [12 empty] | MRC, CRC HQ, CRC BD, CRC FO, AMCROSS, NCDM | bar: Quarter 3 Jul to Quarter 3 Aug
AA6. | Report to OFDA | [12 empty] | MRC | bar: Quarter 1 Jan; Quarter 2 Apr; Quarter 3 Jul; Quarter 4 Oct
B. | Activities for AmCross | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Program Administration and Staff Development
A. | Monitor project implementation and financial expenditure in flood season and non flood season. | [12 empty] | CRC HQ, CRC BD, CRC FO, CRC SBO, AMCROSS, NCDM
B. | Monitor and assist the training provided by FOs to DCDM, CCDM, and RCVs. | [12 empty] | CRC HQ, CRC BD, CRC SBO, AMCROSS, NCDM
C. | Provide quarterly and yearly financial reports to MRC. | [12 empty] | AMCROSS | bar: Jan; Apr; Jul; Oct
D. | Review and create monthly development plans, discuss relevant issues, and share experiences between RCVs and CCDM. | [12 empty] | CRC BD, CRC FO, CRC SBO
E. | Compile information from all branches into a quarterly report and submit to AmCross. | [12 empty] | CRC HQ, CRC BD, CRC FO, CRC SBO | bar: Jan; Apr; Jul; Oct
F. | Prepare for learning visit by Lao partners. | [12 empty] | CRC HQ, CRC BD, CRC FO, CRC SBO, AMCROSS, NCDM | bar: May
G. | Flood Forum Workshop | [12 empty] | CRC HQ, AMCROSS, NCDM | bar: Apr
H. | Participate in donor meetings, arrange and facilitate logistic and accompany donor on site visit. | [12 empty] | CRC HQ, AMCROSS, NCDM
Output 1.1 | Flood Referencing Tools and Methods | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1.1.1 | Develop training curriculum about floods and preparedness with CRC/AmCross/NCDM-EWS based on existing training curriculum by CRC, ACF, and Oxfam GB, including training curriculum for school dissemination. | [12 empty] | CRC HQ, AMCROSS, NCDM | bar: Feb
1.1.2 | Train DCDM, CCDM, and RCVs about floods and flood-preparedness. All trainings will show the DCDM, CCDM, and RCVs how to forecast the local water levels based on the flood markers at each village. Training schedule ranges between 1-3 days per course. This training will be held at the commune level during the monthly meeting. | [12 empty] | CRC FO | bar: Feb to Mar
1.1.3 | During flood season; report flood marker water levels to CRC HQ (RCVs transfer flood marker information to CRC SBOs) | [12 empty] | CRC FO, CRC SBO | bar: Jun to Dec
1.1.4 | Monitor the training of villagers who can read and write to read water level flood markers, water the information on the billboards, and report to their fellow villagers during the flood season. The training will be conducted by the RCVs and CCDM. | [12 empty] | CRC HQ, CRC FO, CRC SBO, AMCROSS, NCDM | bar: Jul to Dec
1.1.5 | Monitor the training of villagers to mark their house poles using as a reference the community flood marker water level and/or the village billboard. The training will be conducted by the RCVs and CCDM. | [12 empty] | CRC HQ, CRC FO, CRC SBO, AMCROSS, NCDM | bar: Jul to Dec
1.1.6 | Conduct flood information dissemination in 38 villages before flood season for flood preparedness and response activities for their crops, animals, livestock etc before flood hit their villages. (can be conducted in pagodas) | [12 empty] | CRC FO, CRC SBO with RCVs | bar: Apr to Jun
1.1.7 | Conduct flood information dissemination in provincial schools before and during flood season when schools are open. | [12 empty] | CRC FO, CRC SBO with RCVs | bar: Apr to May; Aug to Sep
1.1.8 | During floods; Monitor RCVs and CCDM collect information on the effects of flood waters at specified times, gauge heights, and relay the information to the CRC branch or sub-branch in the 38 villages. | [12 empty] | CRC HQ, CRC BD, CRC FO, CRC SBO, AMCROSS, NCDM | bar: Jun to Nov
1.1.9 | RCVs provide project information in the form of questionnaires to households in 38 villages. | [12 empty] | CRC BD, SRC FO, CRC SBO | bar: Jul
1.1.10 | Conduct survey to measure information retention and knowledge of villagers based on information sharing from questionnaires and trainings. | [12 empty] | CRC HQ, AMCROSS, NCDM | bar: Nov
Output 1.2 | Early Warning System Communication Materials | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1.2.1 | Training on use of guidebooks, leaflets, and posters. CCDM and RCVs will explain and distribute the materials during their village meetings, group meetings, and house visits. | [12 empty] | CRC HQ, CRC BD, CRC FO, CRC SBO, AMCROSS, NCDM | bar: Feb to Mar
1.2.2 | Produce video play about the project. The production will be shared with relevant stakeholders. | [12 empty] | CRC HQ, AMCROSS, NCDM | bar: Feb to Mar
1.2.3 | Show mobile video play in all areas before and during flood. | [12 empty] | CRC FO, CRC SBO | bar: Apr to May; Jul to Aug
1.2.4 | Project dissemination with radio stations and the CRC Website. | Jan: Project information will be disseminated throughout the year based on the project progress. | CRC HQ, AMCROSS
1.2.5 | Ensure that CCDM and RCVs maintain and repair billboards and flood markers during the dry and rainy seasons with contribution by villagers. | [12 empty] | CRC FO, CRC SBO
Output 1.3 | Village Contribution | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1.3.1. | Ensure that village committees consisting of monks from Buddhist temples, CCDM members, RCVs, and village representatives function well. | [12 empty] | CRC FO, CRC SBO
1.3.2. | Assist CCDM to develop community fund raising criteria. | [12 empty] | CRC FO, CRC SBO, NCDM
1.3.3. | Ensure that community funds are collected and inform the public the amount of funds received and the amount spent for repairs and maintenance. | [12 empty] | CRC FO, CRC SBO, NCDM
1.3.4. | Repair and maintain flood markers and billboards using community funds. | [12 empty] | CRC FO, CRC SBO, NCDM
1.3.5. | Report community funds received and activities implemented from these funds to AmCross. | [12 empty] | CRC HQ, CRC FO, CRC SBO, NCDM
Output 1. 4 | Community Feedback | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1.4.1 | After the flood season, meet with CCDM, RCVs, villagers, and village leaders to determine lessons learned, successes, and improvements needed in the project for next year activities. These will be reported in the final quarterly report. | [12 empty] | CRC HQ, CRC BD, CRC FO, CRC SBO, AMCROSS, NCDM | bar: Nov to Dec
ARC or AmCross | American National Red Cross
BOs | Brach Officers
CRC | Cambodian Red Cross
CCDM | Commune Committee for Disaster Management
DCDM | District Committee for Disaster Management
DHRW | Department of Hydrology and River Works
EWS | Early Warning System
FAS | Financial and Administration Section of MRC Secretariat
FOs | Field Officers
IEC | Information Education and Communication
PCDM | Provincial Committee for Disaster Management
PRC | Provincial Red Cross
MRC | Mekong River Commission
MRCS | Mekong River Commission Secretariat
PCDM | Provincial Committee for Disaster Management
PRC | Provincial Red Cross
RCV | Red Cross Volunteer
SBOs | Sub-Branch Officers

## CRC project budget 2006
Ref # | Work plan Activity | COST ESTIMATE/BREAKDOWNS
CRC EWS BUDGET
|  | Personnel | Quantity | Unit | Quantity | Unit | Unit Cost | TOTAL | Required from | BUDGETED | CRC | ARC & MRC | Total | Acct Code
[8 empty] | Amount | Project | Amount
[7 empty] | ($) | ($) | % | ($)
CRC
1 |  | CRC Disaster Management Specialist Officer | 1 | person | 12 | months | 347 | 4164 | 100% | 4164 | 4164 |  |  | 54926.1
2 |  | CRC Disaster Management Specialist Assistant | 1 | person | 12 | months | 330 | 3960 | 100% | 3960 | 3960 |  |  | 54926.1
3 |  | CRC Disaster Management Support Accountant | 1 | person | 12 | months | 330 | 3960 | 100% | 3960 | 3960 |  |  | 54926.1
4 |  | CRC Office Assistant | 1 | person | 12 | months | 210 | 2520 | 100% | 2520 | 2520 |  |  | 54926.1
5 |  | CRC Communications Officer | 1 | person | 10 | months | 330 | 3300 | 50% | 1650 | 1650 |  |  | 54926.1
6 |  | CRC Community-based Disaster Management Specialists (Field Officers) | 4 | person | 12 | months | 263 | 12624 | 100% | 12624 | 12624 |  |  | 54926.1
7 |  | CRC Branch Directors | 4 | person | 12 | months | 168 | 8064 | 50% | 4032 | 4032 |  |  | 54926.1
Travel
Allowances
Phnom Penh based Project staff
8 |  | CRC Project Officer, Assistant, Accountant, & Communications Officer | 4 | person | 11 | months | 108 | 4752 | 100% | 4752 | 4752 |  |  | 54926.3
|  | CRC branch directors (flood and non-flood) | [5 empty] | 0
9 |  | Kandal | 1 | person | 12 | months | 57 | 684 | 100% | 684 | 684 |  |  | 54926.3
10 |  | Prey Veng | 1 | person | 12 | months | 46.25 | 555 | 100% | 555 | 555 |  |  | 54926.3
11 |  | Kratie | 1 | person | 12 | months | 27.375 | 328.5 | 100% | 328.5 | 328.5 |  |  | 54926.3
12 |  | Stung Treng | 1 | person | 12 | months | 45.75 | 549 | 100% | 549 | 549 |  |  | 54926.3
|  | Provincial Field Officer (flood and non-flood) | [5 empty] | 0
13 |  | Kandal | 1 | person | 12 | months | 64.5 | 774 | 100% | 774 | 774 |  |  | 54926.3
14 |  | Prey Veng | 1 | person | 12 | months | 41 | 492 | 100% | 492 | 492 |  |  | 54926.3
15 |  | Kratie | 1 | person | 12 | months | 32.5 | 390 | 100% | 390 | 390 |  |  | 54926.3
16 |  | Stung Treng | 1 | person | 12 | months | 57.7 | 692.4 | 100% | 692.4 | 692.4 |  |  | 54926.3
|  | Sub Branch Officers (SBOs) | [5 empty] | 0
17 |  | SBOs in Non Flood Season | 5 | persons | 6 | months | 34.5 | 1035 | 100% | 1035 | 1035 |  |  | 54926.3
18 |  | SBOs in Flood Season | 5 | persons | 6 | months | 64.5 | 1935 | 100% | 1935 | 1935 |  |  | 54926.3
|  | Red Cross Volunteers (RCVs) two per village | [5 empty] | 0
19 |  | RCVs in Non Flood Season | 38 | villages | 6 | months | 41 | 9348 | 100% | 9348 | 9348 |  |  | 54926.3
20 |  | RCVs in Flood Season | 38 | villages | 6 | months | 71 | 16188 | 100% | 16188 | 16188 |  |  | 54926.3
|  | Provincial, District and Commune Committee for Disaster Management | [5 empty] | 0
21 |  | PCDM | 4 | persons | 12 | months | 15.5 | 744 | 100% | 744 | 744 |  |  | 54926.3
22 |  | DCDMs | 5 | persons | 12 | months | 15.5 | 930 | 100% | 930 | 930 |  |  | 54926.3
23 |  | CCDMs | 13 | persons | 12 | months | 15.5 | 2418 | 100% | 2418 | 2418 |  |  | 54926.3
Travel
|  | Cross project visits-travel in country (CRC HQ, CRC branch, RCVs...) | [7 empty] | 0 | 0
24 |  | Flood forum workshop (1 AmCross, 1 CRC, and 1 NCDM) | 2 | persons | 1 | trip | 550 | 1100 | 100% | 1100 | 366.6667 | 733.3333 |  | 54926.3 | 53260
25 |  | Cambodia/Laos Project Exchange (Refreshments & Incidentals) | 1 | persons | 1 | trip | 500 | 500 | 100% | 500 |  | 500 |  | 54926.3 | 53260
Training
#REF!
Supplies
IEC Materials and Village Guidebook
26 |  | Leaflets per household | 11350 | households | 1 | copy | 0.048 | 544.8 | 100% | 544.8 |  | 544.8 |  | 55150
27 |  | T-shirt and cap | 300 | persons | 1 | sets | 4 | 1200 | 100% | 1200 |  | 1200 |  | 55400
28 |  | Raincoat | 80 | persons | 1 | set | 4 | 320 | 100% | 320 |  | 320 |  | 55290
29 |  | Prize gift | 38 | villages | 45 | packets | 0.25 | 427.5 | 100% | 427.5 |  | 427.5 |  | 55290
30 |  | Video Production and distribution | 1 | production | 1 | time | 1500 | 1500 | 100% | 1500 |  | 1500 |  | 59930
3992.3
Office Supplies
31 |  | CRC Office Supplies | 1 | office | 12 | months | 120 | 1440 | 100% | 1440 | 1440 |  |  | 54926.4
Equipment/Office equipment
32 |  | LCD Projector | 1 | piece | 1 | time | 1300 | 1300 | 100% | 1300 |  | 1300 |  | 57160
33 |  | Flood Marker Reinstallation | 15 | piece | 1 | time | 200 | 3000 | 100% | 3000 |  | 3000
34 |  | Car batteries for radios and speaker systems (replacements) | 10 | piece | 1 | time | 55 | 550 | 100% | 550 |  | 550 |  | 57160
35 |  | Video set | 1 | piece | 1 | time | 300 | 300 | 100% | 300 |  | 300 |  | 55130
36 |  | Billboard maintenance | 76 | piece | 1 | time | 5 | 380 | 100% | 380 |  | 380
37 |  | Flood marker maintenance | 133 | piece | 1 | time | 3 | 399 | 100% | 399 |  | 399
38 |  | CRC Office equipment maintenance (comp, printer,..) | 1 | office | 12 | months | 50 | 600 | 100% | 600 | 600 |  |  | 54926.6
Administration
39 |  | CRC Office Rent and Utilities | 1 | office | 12 | months | 450 | 5400 | 100% | 5400 | 5400 |  |  | 54926.7
40 |  | CRC Workmen compensation (24 hrs coverage) | 13 | staff | 1 | time | 55 | 715 | 100% | 715 | 715 |  |  | 54926.1
41 |  | CRC Telephone fees - Landline (IDD) | 1 | time | 12 | months | 135 | 1620 | 100% | 1620 | 1620 |  |  | 54926.4
42 |  | CRC office internet fee | 1 | time | 12 | months | 100 | 1200 | 100% | 1200 | 1200 |  |  | 54926.4
|  | TOTAL | [7 empty] | 97221.2 | 86066.5667 | 11154.6333 | #REF!
#VALUE!
[13 empty] | 97221.2 | ARC&CRC
[13 empty] | #REF! | MRC
2639
[6 empty] | PERSONNEL |  |  |  |  | 32910 | 0
[6 empty] | TRAVEL |  |  |  |  | 42181.5667 | 1233.3333
[6 empty] | TRAINING |  |  |  |  | 0 | 0
[6 empty] | SUPPLIES |  |  |  |  | 1440 | 3992.3
[6 empty] | EQUIPMENT |  |  |  |  | 600 | 5929
[6 empty] | ADMINISTRATION |  |  |  |  | 8935 | 0
[11 empty] | 86066.5667 | 11154.6333 | 97221.2
0