## coordination
Myanmar Red Cross Society
Multi hazards contingency plan
1. Sector:- | Coordination
Objective: | To effectively coordinate and monitor the national and international RCRC emergency response to the disaster
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
Formation of Operation Team at HQ |  | President and EC members | • Activate the contingency plan • Identification of Operation coordinator at HQ level. ToR of Operation Coordinator is attached in annex-A • Formation of operation team( Sectoral Coordinator) at HQ under the convenor of identified Operation Coordinator. MRCS needs to identify shector coordinator. The defined sectors in this contingency plan are Coordination, Volunteers and staff safety, Information Management, Health Services, Relief, Shelter, Wash, logistics and Finance and Administration. ToR of Sectoral Coordinators is attached in annex-A • Locate Operation Coordination office • Dessimination of above information/Decisions to respective Township Branch as well as State/Division along with partners | • Form a management team to review the progress on preparedness measures mentioned in this contingency plan under the convenorship of EC member. Chief Coordinator and all HoD must be part of the management team.Regular test and update of contingency plan is the major role of management team. Identify a person in MRCS/HQ as focal person for Contingency plan. • Regularly review the ToR of Operation Coordinator and sectoral leaders. • Map/identify the quickest and realiable means to communicate township Branch. • Dessiminate adequately about the contingency plan and its way of working.( Translation, one day orientation to G1 Officer and G1 officers need to mobilize to orient 2IC at States/Division level) • Identify possible place for Operation Coordination Office and strengthen its capacity as necessary.
Coordination at Central level |  | Operation Coordinator and Operational Team( Sector Coordinators) | • Establish communication with IFRC, GoUM and UNOCHA-Operation Coordinator • Establish communication with respective Sectors at central level- Sector Coordinator • Establsih regular communication with 2IC- Information management sector coordinator and Operation Coordinator. • Regular meeting of Operation Team • Regular reporting to President and EC members to develop strategies as per developing context. | • MRCS needs to communicate its exsiting preparedness level as well as plan to respective ministry and partners periodically. • MRCS needs to make sure their participation in IASC contingency plan task force regularly. • MRCS needs to make sure their participation in different sectoral meeting at central level. • MRCS needs to give continuety of Head of Divisions and Deputy head of division meeting to exchange the progress and challenges to implement this contingency plan effectively in case of emeregency.
Coordination at local level |  | Respective 2 IC of Township Branch | •Establish communication with GOUM, UN, and other agencies operating in the affected areas. • Establish regular communication with Operation Coordinator and sector coordinators. • Establish communication with trained human resources of MRCS at Township Level. • Establish Communication with Township Red Cross supervisory board regularly. | • MRCS Township Branch needs to communicate its exsiting preparedness level as well as plan to local authority periodically. • MRCS Township Branch needs to make sure their participation in different coordination forum at Township Level. • MRCS Township Branch needs to meet periodically to review the preparedness plan. • MRCS Township Branch need to update records of trained HR at township level in coordination with GIS Officer at MRCS/HQ. • MRCS Township Branch needs to organize an interaction session among Trained HR at Township level at least once in a year.
Reporting |  | Sector coordinators, Operation Coordinator, 2 IC and Information focal person at Township level( Ref:- Information Management sector). | • Reporting back to sector coordinator of information management. | • Develop stanadard reporting format and identify means of communication.

## Annex-A
ToR for Operation Coordinator
 S/he is entirely responsible to make effective management and coordination of operation, from the initial emergency response phase. This includes guidance, coaching, facilitating, direction to all sector coordinators and report back to MRCS leadership about the progress of operation as well as to develop next strategies as per changing context.  S/he provides a mechanism for the harmonisation of response efforts across a range of sectors.  S/he responsible to coordinates with other elements of the RCRC Movement (the Federation, ICRC and PNS’s), the authorities, UN agencies, and other humanitarian bodies  S/he responsible to mobilize all support sectors like Logistics, Finance and Admin, Information management along with security of staff and volunteers.  S/he responsible for reporting as well as preliminary and emergency appeal to handle the operation effectively.  S/he responsible to continuously monitor and assess the progress of the ongoing DR.
ToR for Sector Coordinators
 The sector coordinators need to support Operation coordinator for effective management as well as coordination of their defined sector from the initial emergency response phase. This will include HR and other logistics support.  The designated coordinators are responsible to lead their defined sector in close coordination with Operation coordinator as mentioned in contingency plan matrix.  The designated coordinators need to provide his/her support to Operation Coordinator in order to establish mechanism for the harmonisation of DR efforts across a range of Sectors.  The designated coordinators are responsible to ensure that reporting obligations as well as continuous monitoring and feedback to Operation coordinator as well as operation team to redefine operation strategies as per needs.  The designated coordinators are responsible to participate at respective coordination forums and provide required inputs in order make systematic response operation.

## volunteers and staff safety
2. Sector:- | Volunteers and Staff safety
Objectives:- | To ensure as far as possible the safety and security of disaster affected MRCS staff and volunteers involved in the response operation
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
Volunteers safety |  | Operation Coordinator, DCU Coordinator and 2 IC of respective township | • In severe case, Operation Coordinator needs to coordinate with central authority to rescue of any trapped volunteers. • In general case, 2IC needs to coordinate with local authority to rescue of any trapped volunteers. • Operation Coordinator needs to coordinate with IFRC to implement insurance guidelines. • 2 IC needs to mobilize trained volunteers/staff locally for psychological support for required volunteers at safe locations and facilitate process to tranfer in nearby health institution. • 2 IC needs to mobilize trained volunteers/staff locally for First Aid and triage of any casualties and evacuation as necessary for volunteers. | • Mapping of government and other partners who have expertise in search and rescue and establish coordination with them at central as well as local level. • Develop an insurance guidelines along with IFRC for volunteers. • Data base of Trained PSP at Township level and establsih contact periodically with them with refresher. • Data base of Trained FA at Township level and establsih contact periodically with them with refresher. • Develop security guidelines for volunteers
Staff safety |  | Operation Coordinator and 2 IC of respective township | • In severe case, focal person of operation needs to coordinate with central authority to rescue of any trapped staff . - In general case, 2IC needs to coordinate with local authority to rescue of any trapped staff. •Operation Coordinator needs to coordinate with IFRC to implement insurance guidelines. • 2 IC needs to mobilize trained volunteers/staff locally for psychological support for required staff at safe locations and facilitate process to tranfer in nearby health institution. • 2 IC needs to mobilize trained volunteers/staff locally for First Aid and triage of any casualties and evacuation as necessary for staff. | • Mapping of government and other partners who have expertise in search and rescue and establish coordination with them at central as well as local level. • Develop an insurance guidelines along with IFRC for staff. • Data base of Trained PSP at Township level and establsih contact periodically with them with refresher. • Data base of Trained FA at Township level and establsih contact periodically with them with refresher. • Develop security guidelines for Staff.
Reporting |  | Sector coordinator for shelter, Operation Coordinator, Sector coordinator for information management, 2 IC and Information focal person at Township level. | Reporting back to sector coordinator of information management. | Develop stanadard reporting format and identify means of communication.

## information management
3. Sector: | Information management
Objective:- | To collect accurate and relevant information on emergency needs to process and desseminate it effectively
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
Collection of damage, loss, and needs data at local level and transmission to Operation Coordination Office |  | Operation Coordinator, Information Management Sector coordinator and 2 IC | • Township Branch needs to identify Township level information focal person and other trained person for rapid assessment. • Township Branch needs to mobilize immediately above said person to collect emergency data using standard formats and feed to operation coordination office. • Township Branch needs to establish contact with local authorities and other agencies operating in the area • Operation Coordinator needs to explore all possibilities to equip affected township Branch as well as Operation Coordination Office | • Identification of 2 focal person( Selected brigade could be best for this purpose) at Township Level for information management. • Training for such people about tasks in case of emergency. • Maintain regular contact with relevant partners and authorities at local as well as central level. • Map in advance the appropriate communication equipments for Township as well as central level. • Stanadardization of Rapid assessment format. • Strengthen MRCS communication Division.
Deployment of Rapid Assessment Team to affected areas |  | Operation Coordinator and Operation Team | • Deployment of Multi-sectoral Rapid Assessment Team as soon as possible after the onset of the disaster. • Rapid Assessment Team feeds data to Information management sector coordinator to facilitate preparation of initial Plan of Action (POA) and Emergency Appeal (EA) | • Maintain data base of DART members at Central as well as respective Township. • Refresher for selected DART members. • Train more people on RDRT and NDRT( Identify potential Brigade and others for same purpose) from states/division level. • Orient all concerned on Rapid Assessment format. • Finalize roaster for rapid assessment team at States/division level and review that roaster periodically.
Compilation and dissemination of information |  | Information management sector coordinators needs to take lead and other operation coordination team need to back up. | • Monitoring of all relevant information sources (media, NGOs, government agencies, etc.) • Sharing information to President, EC members and Operation Coordination Team. • Data and field reports shared regularly with Federation and other organizations as relevant. • DMIS up-dated on a regular basis. • Draft PoA / preliminary International Appeal disseminated with Operation Team, President as well as EC members for their feedback. • Information Bulletins and Operations Updates prepared as needed. • Data / information shared with GOUN, UNOCHA, and other actors. | • Identify at least 2 people in advance to prepare information bulletins, operation updates, monitoring all relevant information from different sources at MRCS/ HQ as well as enhance their capacity on same. • Consider GIS Officer as DMIS Officer for time being and enhance capacity for same. • Identify at least 2 people to develop POA/preliminary international appeal in advance and enhance their capacity on same.
Media relations |  | Sector coordinator of Information Management, Operation Coordinator, President and EC members | • Contact established and maintained with local, regional and international media. • Identify dedicated spokesperson for emergency operations and contact number. • Key messages identified relating to emergency response operation. • Q&A prepared for use by spokesperson and key responders. | • Develop roaster of available media in MRCS/HQ. • Develop skills of few people of MRCS/HQ in dealing media.
Reporting |  | Sector coordinators Operation Coordinator, 2 IC and Information focal person at Township level. | Reporting back to sector coordinator of information management. | Develop stanadard reporting format and identify means of communication.

## RFL
4. Sector: | Restoring Family Links
Objective:- | To reestablish family links between family members separated by disaster
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
RFL activities launched within 24 of disasters |  | RFL Coordinator and state/district level RFL focal persons | • Deployment of RFL team to undertake assessment • Identification of target areas, coordination roles, communication methods, tools, data management system to be used to reestablish family links • Mobilisation of volunteers to support RFL response, inform affected population of RFL service • Dissemination about RFL service to affected population through government broadcast system under Ministry of Information and other public mass media means. • Commencement of registration and other RFL activities (according to identified tools and criteria) within 24 hours after disaster. The most vulnerable such as unaccompanied children, unaccompanied single women, elderly, sick and disabled must be considered as first priority for tracing requests. | • Identification of RFL tools and procedures. • Mapping of RFL focal persons at state/district levels and enhancement of skills. • Training of staff and volunteers in RFL tools and procedures. • Negotiation of clear roles and responsibilities with government agencies, local and international organisations. • Mapping of means of communication at local levels. • Pre-stock of printed RCM forms and RFL emergency kits at MRCS headquarters available for deployment. • Strengthen personal data management and protection system.
Reporting |  | RFL Sector coordinator , Operation Coordinator, Information Management Sector coordinator, 2 IC and Information focal person at Township level. | • Reporting back to Operation coordinator and Information Management sector coordinator. | • Develop stanadard reporting format and identify means of communication.

## Health services
5. Sector: | Health Services
Objective:- | To provide immediate rescue and medical assistance and longer term emergency health services to the disaster affected population
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
Psychosocial support Service(PSP) |  | Training Division, 2 IC and PSP Team | • Identification location for mass/individual PSP support. • Deployment of PSP team from Township level to identify potential beneficiaries for PSP support. • Commencement of PSP activities as soon as possible after disasters by mobilizing PSP team. • Mobilization of volunteers to inform affected population about how to access PSP support. Most vulnerable groups like unaccompanied minors, unaccompanied single women, elderly, sick and disabled need to consider as first priority. • Refer the serious people in near by health centre for PSP support. | • Map the possible location at most vulnerable areas of township where mass or individual PSP support can provide. • Identification of around 5 MRCS volunteers( Selected brigade could be best for this purpose) as PSP team at Township level and update data base in MRCS/GIS System. • Conduct PSP training and refresher for identified MRCS PSP team members periodically. • Map the possible health centre where PSP support available. • Develop Referal guidelines and share the concerned team.
First Aid services |  | 2 IC and FA team at Township level | • Identification location for FA support. • Deployment of Trained Brigade and FA team from Township level to identify of people for FA support. • Commencement of FA activities as soon as possible after disasters by mobilizing FA team. • Mobilization of volunteers to inform affected population about how to access FA support. Most vulnerable groups like unaccompanied minors, unaccompanied single women, elderly, sick and disabled need to consider as first priority. • Refer the serious people in near by health centre for support. | • Map the possible location at most vulnerable areas of township where FA support can provide. • Identification of around 25 MRCS volunteers(Selected brigade could be best for this purpose) as FA team at Township level and update data base in MRCS/GIS System. • Conduct FA training and refreshers for identified MRCS FA team members. • Map the possible health centre. • Develop Referal guidelines and share the concerned team.
Hygine promotion |  | Township Supervisory Board, 2IC and community volunteers | • Generate awareness to promote practicing hygine food preparation and storage as well as cleaning all kitchen utensils. • Promotion of health practices by mobilizing different volunteers as well as school children at disaster affceted areas. • Distribute IEC materials to promote hygine promotion. | • Stand by hand mikes at Township level to inform affected population about good heath practices. • Development of relevant IEC materials and stocks at Township Branch. • Develop relation/communication with community people of most vulnerable areas. • Identify few brigade as focal person for awareness generation along with communities.
Facilitate the deployment of incoming global emergency health tools (Field Hospital and Basic Health Care ERUs, etc.) |  | Operation Coordinator and Health services Sector coordinator | • In consultation with local authorities, identify unmet needs in terms of emergency health care provision and ensure that global Movement mobilises appropriate ERUs. • With local authorities, identify and prepare optimum sites for installation of ERUs on arrival, to facilitate rapid start-up. • Ensure efficient set-up of ERUs and integration into ongoing provision of emergency health services. • Monitor ERU operation and at appropriate time initiate arrangements for ERU phase-out. | • Coordination and consultation with IFRC and movement partners • Participate different Health Services coordination forum in Central level
of incoming global
emergency health tools
(Field Hospital and Basic
Health Care ERUs, etc.)
Reporting |  | Shelter Sector coordinator , Operation Coordinator, Information Management Sector coordinator, 2 IC and Information focal person at Township level. | Reporting back to sector coordinator of information management. | Develop stanadard reporting format and identify means of communication.

## Relief
6. Sector: | Relief
Objective:- | To rapidly provide appropriate relief items to individuals and families affected by the disaster
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
Review information available as a result of rapid assessment report |  | Information Management Sector coordinator , Relief Sector Coordinator , Operation Coordinator, 2 IC and information focal point at Township Level(refer Information management sector) | • Compile and review information arriving from MRCS Township Branch. | • Update date base of trained HR( especially DART as well as RDRT) in MRCS/Hq as per Township. • Develop the Rapid Assessment checklist as well as procedure to mobilize the trained HR. • Map possible locations which can be considered as operation office at Township level. • Conduct NDRT training to secure at least 5 people( Selected brigade could be best for this purpose) at each states/division level. Develop ToR for NDRT. • Refresh trained HR periodically. • Orient Township Level Information focal person( Selected brigade could be best for this purpose) about rapid assessment as well as process of compilation. • Map possible means of communication and explore possibilities to equip Township Branch on same.
Verify the information with partner |  | Information management Sector coordinator , Relief Sector Coordinator , Operation Coordinator, | • Ensure regular communication with partners and GOUM to confirm needs | • MRCS needs to establish their communication with relevants sectoral meeting at centre.
Verify the availability and accessibility of existing DP stock in the aftermath of the disaster |  | Relief Sector coordinator, Grade-1 Officer and warehouse focal person in MRCS/HQ | • Update DP stocks reports received from warehouse officer | • Strengthen States/Division level warehouse capacity in terms of warehouse management, warehouse capacity and communications.
Confirm the availability of vehicles to transport relief supplies to distribution counters |  | Transport Incharge and Relief Sector Coordinator as well as Logistics Sector Coordinator | • Review list of selected transporters in centre as well as states/divisions level with cost, and identify those still operational. • Confirm availability of running conditions MRCS transport assets. | • Make framework agreement with available transport company at centre as well as states/divisions level. • Make a system to review MRCS fleet conditions periodically.
Confirm the total DP stocks (existing plus procured and other sources) available for emergency response |  | Operation Coordinator and Sector coordinator for Relief and warehouse focal person in MRCS/Hq | • Confirmation of DP stocks at identified warehouses. • Procurement of supplies as mentioned in MRCS’s special procurement provision in case of disaster. • Ensure adequate stock assigned to Relief ERU( if present) • Following supplies will consider as first relief items for per affected family:- a) Kitchen set-1 set (b) Male Loongi-1pcs (c) Female loongi-1 pcs (d) Blanket- 2 pcs (e) Mosquito net-1 pcs (f) Shirt+half Trousers-1 set (g) Skirt+Blouse-1 set. | • Establsih a regular reporting system from different warehouses of the country. • Develop special procurement policy and guidelines to speed up the procurement process in case of emeregncy. • Communicate partners regular.
Coordinate the management of relief distribution at the district level. |  | Releif Sector Coordinator for Relief and 2 IC | • Identify twonship level relief focal person in all affected sites. | • Select at least five person as focal person( Selected brigade could be best for this purpose) for relief at States/Division level and enhance the capacity of same. • Map the trained HR of the Township level and refresh them on assessment, relief distribution, coordination and reporting.
Organise effective relief distribution |  | 2IC and Relief Focal person | • Identify the focal warehouses at field level for smooth relief operation. • Maintain proper supply chain. • Identify distribution site to effective and transparent distribution. • Identify MRCS volunteers as distribution monitor for each distribution site. • Share final distribution list and items with partners in the affected area to avoid duplication. • Share the distribution date and distribution counters information to beneficiaries and their representatives. | • Map MRCS volunteers who can work as distribution monitor( Selected brigade could be best for this purpose) at Township level. • Explore all possibility to organize training/refresher course for them on distribution. At least 1o people at each Township level. • Identify the means to communicate beneficiaries about distribution and enhance MRCS Township Branch for same. • Identify few volunteers( Selected brigade could be best for this purpose) at states/Division level, who can work as warehouse focal person in case of emergency and enhance their capacity for same.
Carry out effective relief distribution |  | 2IC and Relief Focal person | • Reconfirm beneficiary lists. • Identify and mobilize MRCS volunteers at each distribution site. • Verify each beneficiary’s identity. • Distribute relief materials to identified beneficiaries. • Verify final distribution list and cross-check with stock list. • Secure distribution site and return remaining relief materials stock to designated warehouses. • Report on distribution to Relief Sector Coordinator. | • Map MRCS volunteers who can work as distribution monitor ( Selected brigade could be best for this purpose) at Township level. • Explore all possibility to organize refresher/training course for identified possible distribution monitor on distribution.At least 1o people at each Township level. • Identify the means to communicate report to Relief Sector coordinator.
Retain overview of relief activities and mobilize additional inputs as necessary |  | Operation Coordinator and Relief Sector coordinator, 2IC and G1 Officer | • Monitor needs versus immediately available resources. • Trigger procurement activities as necessary • Mobilise additional relief stocks from non-affected areas. • Mobilise global relief inputs through International Appeal. • Mobilise Relief ERU as necessary | • Develop specail Procurement policy and procedure for emergency. • Framework agreement provisions with suppliers. • Establish Emergency fund at MRCS and guidelines of its mobilization.. • Continuous coordination with IFRC and other movement partners.
Reporting |  | Relief sector coordinator , Operation Coordinator, Information management Sector coordinator 2 IC and Information focal person at Township level. | Reporting back to sector coordinator of information management. | Develop stanadard reporting format and identify means of communication.

## E.Shelter
7. Sector: | Emergency Shelter
Objective:- | To determine and meet immediate post-disaster shelter needs
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
Rapid assessment of emergency shelter needs |  | Shelter Sector Coordinator , Operation Coordinator and 2 IC | • Estimate number of homeless due to disasters, according to all available sources of information. • Determine immediate needs in terms of shelter, to include: open air sites / communal building sites / other specific needs according to season. • If required, and if sufficient personnel available, participate in assessment of damage and needs in related fields such as impact of disasters on schools and other educational facilities • Estimate extent of damage to buildings and broadly assess safety of remaining structures. • Estimate needs in terms of essential household items and fuel for cooking / heating. | • Identification of emergency shelters settlement safe locations with basic facilities in collaboration with respective ministries and agencies concerned at most of the vulnerable areas of the country.
Liaison with RCRC and other partners for effective emergency shelter response |  | Shelter Sector Coordinator and Operation Coordinator | • Coordinate with Federation to mobilize Federation shelter coordination team. • Mobilize MRCS trained/experienced personal for Shelter support. • Update data base of beneficiaries. • Distribution of standards and guidelines for emergency shelter. | • Identification of actors involved in emergency shelter along with assessment of their capacities, including disaggregation of those with experience and presence. • Update Data base of trained/experienced MRCS human resources. • Maintain communication with shelter counterparts at GOUM, UNOCHA, I/NGOs • Conduct training and refresher course for MRCS concerned volunteers( Selected brigade could be best for this purpose) and staff at States/Division Level to enhance MRCS shelter capacity.
Distribution of emergency shelter item |  | Shelter Sector Coordinator , Operation Coordinator and 2 IC | Distribution of two tarpaulins to each identified HH. MRCS can go with specific NFRI as mentioned in IASC Shelter response plan if possible. | Pre-positioning of Tarpaulins(2 pcs/HH) for emergency shelter for the agreed number of HH
Reporting |  | Shelter Sector coordinator, Operation Coordinator, Information Management Sector coordinator, 2 IC and Information focal person at Township level. | Reporting back to sector coordinator of information management. | Develop stanadard reporting format and identify means of communication.

## Wash
8. Sector: | WASH
Objective:- | To ensure that adequate water and sanitation facilities are provided for the disasters affected people
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
Identify most needy place for WASH |  | 2 IC, selected volunteers and assessment team and Sector Coordinator-WASH | • Coordinate with local and other partners for resources to distribute water. • Mobilize available three WASH-Kits from the support of trained HR of MRCS. • Dustribute chlorine tablets as well as other means to ensure access of safe water. • Coordinate with other partners for water collection pot if needed or distribute water collection pot if possible. • Distribute water as agreed standard and quantity from preinformed distribution counters. | • Identify partner at Township level for WASH. • Form team( Selected brigade could be best for this purpose) to manage existing WASH-Kits. • Develop a schedule to check existing WASH-kits tools • Training and refresher to selected volunteers( Selected brigade could be best for this purpose) at each states/Division level • Data base of such trained person with respective G1 and GIS Officer, MRCS/Hq
Need analysis and coordination with movement global mobilization |  | 2 IC, selected volunteers ,Operation Coordinator and Sector Coordinator-WASH | • In consultation with local authorities, identify unmet needs in terms of water, sanitation, and hygiene provision, and ensure that global Movement mobilises appropriate ERUs. • With local authorities, identify and prepare optimum sites for installation of ERUs on arrival, to facilitate rapid start-up. • Ensure efficient set-up of ERUs and integration into ongoing provision of emergency water, sanitation, and hygiene services. • Monitor ERU operation and at appropriate time initiate arrangements for ERU phase-out. | • Coordination and consultation with IFRC and movement partners • Participate different WASH coordination forum in Central level
Carry out dissemination of safe hygiene practices information |  | Township Supervisory Board and 2IC | • Generate awareness to promote practicing hygine food preparation and storage as well as cleaning all kitchen utensils • Promotion of health practices by mobilizing different volunteers as well as school children at disaster affceted areas • Distribute IEC materials to promote hygine promotion. | • Stand by hand mikes at Township level to inform affected population about good heath practices. • Development of relevant IEC materials. • Develop relation/communication with community people of most vulnerable areas. • Identify few brigade as focal person for awareness generation along with communities.
Reporting |  | Sector coordinator for WASH, Operation Coordinator, Sector coordinator for information management, 2 IC and Information focal person at Township level. | • Reporting back to sector coordinator of information management. | • Develop stanadard reporting format and identify means of communication.

## logistics
9. Sector: | Logistics
Objective:- | To ensure effective logistical arrangements and transport facilities are in place to support the disasters response operation
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
Mobilisation of available logistics assets |  | Operation Coordinator, Logistics Sector Coordinator and 2 IC | • Identify MRCS ready to move vehicle and placed at disposal of Operation Coordination Team. • Coordinate with other movement team to explore fleet and see possibility to develop system to mobilize fleet joinly. • Explore all possibility to pool fleet belongs to MRCS and movement partners from non disaster affected areas to affected areas | • Close monitoring system regarding fleet condition and repair as soon as possible. • Develop a standard concept within movement to run logitics. • Conduct Logistics Training to secure at least 5 people( Selected brigade could be best for this purpose) at each States/Division level.
Mobilisation of global Movement logistics assets |  | Operation Coordinator and Logistics Sector Coordinator | • Coordinate with Federation to mobilize logistics global resources. • Logistics ERU mobilised with air-ops element if necessary • Federation RLUs advised of response operation requirements in terms of vehicles and temporary storage facilities (e.g., Rubb Halls) and requested to mobilise same • On-site preparations for installation of Logistics ERU and temporary storage facilities • GOUM requested urgently to facilitate arrival of relief goods and logistics assets | • Maintain regular contact with respective ministry of government and if possible reach into an agreement to get relief goods into country quickly. • Coordination and consultation with IFRC and movement partners • Participate different Logistics coordination forum in Central level
Reporting |  | Logistics Sector coordinator , Operation Coordinator, Information management Sector , 2 IC and Information focal person at Township level. | • Reporting back to sector coordinator of information management. | • Develop stanadard reporting format and identify means of communication.

## Finance & Admin
10. Sector: | Finance and Admin
Objective:- | To provide efficient financial, administrative, and human resources support to emergency operations.
Action points |  | Responsibility | Specific tasks in case emergency | Preparedness measues at normal time
Release emergency funds for affected Township to make field operation smooth |  | Operation Coordinator, Finance and Admin Sector Coordinator and 2 IC | • Identify professional to deal emeregncy fund at centre as well as Township level. •Managing account system at Township level as well as central level. | • Develop Roaster of people who can deploy for accounting ssyetm at Township level for the period of contingency plan. • Develop a standard accounting system to deal emeregncy. • Generate fund at HQ level as emergency fund, which can be mobilized for assessment, rescue and transportation as well as some dry food.
Mobilise global funding for emergency operation |  | Operation Coordinator and sector coordinators | • Assist in preparation of budget for DREF application • Assist in preparation of Federation Preliminary Appeal / RevisedAppeal • Maintain up-to-date financial reporting of emergency operations • Open separate bank account as necessary | • Orient conerned people on DREF as well as preliminary and emeregncy appeal.
emergency operations
Participate in national fundraising activities- (PLEASE discuss within MRCS. This is one of the most important action usually NS face during disasters and need to have some strategies for normal time as well) |  | Operation Coordinator, sector coordinators and resource mobilization person | • Put in place financial support mechanisms for national fund-raising activities. • Maintain transparent accounting procedures. • Contact and coordinate with fund-raising partners (e.g. banks / national companies, etc.) | • Identify Resource mobilization person. • Develop policy for resource mobilization. • Map the potential companies and individual for resource mobilization.
Prepare to receive external delegates |  | Operation Coordinator and sector coordinators and Head International relation Unit | • Make necessary arrangements for visas / letters of invitation. • Coordinate with IFRC country delegation to arrange possible accommodation. • Identify and arrange for dedicated office space. • Ensure smooth functioning of welcome service (airport pick-up / information pack / security rules) • Keep up-to-date contact list and location of in-coming staff (i.e.international delegates/ FACT / ERUs/ RDRT / NDRT, etc.) and circulate. • Have stock of SIM/phone cards for in-coming staff in possible extends. | Review this sector periodically and feedback to Contingency Plan focal person to update accordingly.
Provide administrative and HR support to operations |  | Operation Coordinator and sector coordinators | • Assist in setting up of office for Operation Coordination Office. • Manage smooth functioning of office (personnel, material, human resources, facilities) | Review this sector periodically and feedback to Contingency Plan focal person to update accordingly.
Coordinate with international operations |  | Operation Coordinator and sector coordinators | • Provide necessary back-up and information exchange with Federation operations once established. • Assist in immediate staffing and hiring of additional local staff. • Share standard salary and per diem rates / local contract format with in-coming international personnel (e.g. Federation / ERUs /RCRC bi-laterals). | Review this sector periodically and feedback to Contingency Plan focal person to update accordingly.
international operations
Reporting |  | Sector coordinators , Operation Coordinator, | Reporting back to sector coordinator of information management. | Develop stanadard reporting format and identify means of communication.