## LFM(EWS06)
Cambodian Red Cross
Flood Early Warning System
LOGICAL FRAMEWORK PLANNING MATRIX FOR CRC-EWS PROJECT 2006-2007
Narrartive Summary | Indicators | Sources of Verification | Assumption
Goal. Reduced the risk of vulnerable communities in Cambodia to higher-than-normal annual floods. | Impact: % decrease in risk (which can be measured by any or all of the following: decrease in vulnerability, decrease in hazards and/or increase in capacity) | Baseline and final surveys, focus group discussions and quarterly & annual reports | - High commitment/ suitable human resources in implenting the project
Objective. Flood Early Warning methods and protocols attained, enable flood- vulnerable populations in LMB Cambodia to effectively response to flood risk. | Impact: % communities that can interpret EWS warnings. Monitoring: - No. communities receive and understand warnings within desired timeframe. - % decrease in community response time to flood warning | Baseline & final surveys on effectiveness, Focus group discussions and quarterly & annual reports | - EWS-HQ provide materials,methods and protocol for community involvement.
Output 1.1- Flood Referencing tools and Methods | Impact: % project villages with at least two provided tools associated with local made tools. Monitoring: No. of flood-referencing tools (i.e water gauges) local produced. No.of communtiy members trained on flood data collect. No.of flood affected households perform flood prepareness and response activities. | RCVs'log book. Monthly Data recording. Community feedback. Quarterly and Annul reports; Routine Community Monitoring | - Active participation of local authority, key persons and community in implementation. - Communities are willing to share information routinely. - Communities are able to take flood response activities on-time.
Output 1.2- Early Warning System Communication Materials | No.of community members that can interprete EWS pamphlets and project demonstration
Output 1.3- Village Contribution | No. of contribution shared by communities.
Output 1.4- Community Feedback | - % communities providing feedback - % communities can take flood response activities. - No.communities participate in lessons learned meeting and improvement.
Interventions | Activities | Resources | Preconditions
Enhancement the management | Inter-Project Cross visit for EWS implementers |  | Technical assistance
capacity of implementers | Monthly meeting for capacity-upgrading, discussion relevant issues, share experiences and develop plan. |  | from MRC/ARC
| Meeting with relevant partners. |  | CRC-DMD
Attend specific training for HQ staffs
Output 1.1 | Train DCDM, CCDM, and RCVs, at the commune level, about: floods and flood-preparedness, forecast the local water levels based on the flood markers at each village. |  | Project pamphlets Availability of local low- cost materials
Conduct project dissemination in 38 villages before flood season for flood preparedness and response activities.
| Conduct dissemination, on flood mark reading and updating billboard, in community school children and literate adults before and during flood season. |  | Availability of office facilities
Conduct using flood referencing tools to villagers, in flood season and recirculate the information within village.
| Establishment of house pole flood mark reference to village's tools before flood hit the communities. |  | Other methodologies
| In flood season, Collect information of flood level, its impact. |  | and tools.
Demonstration the project pamphlets,video, audio to community during meetings, and/or house visits, before and during flood season.
Project dissemination with radio stations and the CRC Website.
Output 1.3 | Orgnize a Project Support Committee in each target village that consisted of authority, key persons and RCVs
PSC mobilize the contribution/ participation of community in project extension and improvement.
Flood referencing tools and project IEC materials repair and maintenance
Output 1.4 | Perception monitoring through questionnaires
Feedback survey on effectiveness of information disse-mination and the recent flood response.

## KPI(EWS06)
Key Performance Indicators for Flood Early Warning System
Objectives | Performance questions | Information Needs and Indicators
Goal. Reduced the risk of vulnerable communities in Cambodia to higher-than-normal annual floods. | What improvement have been made as a result of receiving flood early warning system? | Hydrograph management. Structural flood proofing.
Objective. Flood Early Warning methods and protocols attained, enable flood- vulnerable populations in LMB Cambodia to effectively response to flood risk.
Output 1.1- Flood Referencing tools and Methods | How many households produce home flood mark? How many percents of villagers can collect flood data, in dry and flood season? How many household have prepared for flood hazard? How? How many family respond to flood hazard? How? | No. of home/ own-field floodmark. No.of trainees on flood referencing tools and involvement. Preparation done before flood. Household/population affected by flood and their activities.
Output 1.2- Early Warning System Communication Materials | The capacity of EWS disseminator evaluated by villagers? How many villagers can translate IEC tools? How well community can call up EWS demonstration? | Rating for RCVs/ PSC in dissemination. No.of population receive dissemination. No. of school children (grade 4th and up) receive training. Rating the perception of community on demonstration.
Output 1.3- Village Contribution | How effectively community support to PSC? What are contributions shared by communities? What and how to manage those contributions? | No. of PSC and its function. Type of contribution convertible to cost. Specification of item spent and cost.
Output 1.4- Community Feedback | Who are participating in lesson learnt meeting? How many household established flood response tools? What other flood referencing tools needed? | Name & role of paticipants. % of household established safety area. Comments on other flood referencing tools needed.