## EWS-B
| Task | Description/Iscription | Who's responsible | Completed? | Notes
1 | Budget | Confirm budget available and financial flexibility for the training/workshop |  | Yes No
2 | Date | Number of training days is set for 7: date must be 4-6 weeks after community has started collecting data |  | Yes No | Check with all stakeholders prior to GRCS finalizing.
3 | Participation | Make list of all participants including visitors, etc. coming from beyond the region, etc. |  | Yes No | Note: refer to advice on selection of EWS Workshop participants.
4 | Venue | Identify availability of appropriate conference-type venue and make reservations. |  | Yes No | Note: confirm adequate availability of electtricity and lighting, and back-up plans.
5 | Lodging | Identify availability of appropriate lodging and make reservations for those in need |  | Yes No | Includes hotels in transit for those coming in on international tickets.
6 | Breaks/meals | Decide what snacks, meals and drinks are needed, and contract company to organize these |  | Yes No
7 | Invitations | Make sure all participants are informed (with enough advance notice to procure their visas/tickets, etc.), and confirm their full participation |  | Yes No | Do not forget symbolic government or other "invitees" for opening and closing ceremonies.
8 | Materials and equipments | Decide what is needed and plan how to make it available on time at workshop site. |  | Yes No | Need: LCD, flip charts, markers, tape, printer/photocopy machine and binders for all participants.
9 | Agenda | Prepare a detailed agenda covering all workshop days. | LEZLIE | Yes No | I'll be working on this over next 3 weeks…
10 | Technical content | Prepare and provide the technical content of each session (7 days: 3 ToT and 4 community) (using ToT trainers as in EWS/A). | LEZLIE | Yes No | Will provide to 4 Trainers at least 2 weeks before the start of the Prep sesssion.
11 | Certificates | Prepare two types of certificates for each participant (AT and ComP): formal one with IFRC logo and possibly a second one that is playful (with humour). Organize how to identify/choose who gets each humorous one (voting? Support group decision only?). Procure/print/plan for these. Assist in the final distribution (closing session). |  | Yes No
12 | Team and partner composition | Divide expected participants into appropriate teams (For B, it is: 1. Data-to-Action; 2. Commmunication and 3. Response) and into appropriate mentor/mentee (AT/ComP) pairs. |  | Yes No | Very important: this activity requires confirmation of participants but must be done before they arrive. It also requires decent knowledge of participant profiles and personalities (literacy, experience, etc.). Work closely with Buba and his team. This is not random sampling, but very intentional!! Apply lessons learned from EWS/A.
13 | Information packets | Work with the Red Cross Society ahead of time to confirm that each participant has an appropriate training binder (ToT and ComP should be different). Oversee getting the final version of materials from Lezlie in time to reproduce them before each session/day. Plan with the Red Cross Society team for its preparation and photocopying, etc. Organize the distribution. |  | Yes No | This depends on receiving final version from Lezlie --so keep bugging me to get these!!! EWS/A participants wanted these earlier, so let’s try harder.
14 | Trainig props | Decide what motivational and other training props (maps, signs, balls, noise makers) are needed and plan to have them ready. |  | Yes No | Trainers: bring props you like for your or any other sessions, etc.
15 | Team competition and awards | Prepare and update daily a tally sheet to monitor team scores for each Scored Activity (Lezlie will advise on which activities are to be scored). Feel free to make daily announcements of who's in first, encouraging the teams in last, etc. Grade team-work and organize appropriate neutral judges, when needed. Announce the winners on last day and organize who gets what prizes! |  | Yes No | Support contribution to the symbolic ($1 max) amusing "prize bag" would be appreciated. In EWS/A, members of every team got at least 1 T-Shirt and an "EWS" prize (posters, trinkets, magnets, etc) , depending on team score). Norbert/Marjorie: do we also have any budget for Tshirts/etc?
16 | Field visit | Decide if/when you need a site visit in the agenda, clarify objectives and make logistic plans/arrangements for this |  | Yes No
17 | Reality check | Plan how to touch base regularly with participants with special needs (i.e., semi-literate, etc.) and more generally with other participants. Guide this process. |  | Yes No | In EWS/A it worked very well to have AT/CP pairs discuss every evening and feed back in our daily TOT sessions.
18 | Note-taker and photgrapher | Decide if this training requires note-taking and if so, delegate someone. This could include a flip-chart summarizing "Points to be Concluded Later", "Lessons Learned"….Take photos of group work and make available for archives. |  | Yes No | We definitely need note-taking during the ToT Sessions every evening.
19 | Time-keeper | Decide how best to keep time; delegate to the participant responsible; make sure someone is keeping time and reminding leaders, at every session. |  | Yes No | Often helps to plan for this on a rotational basis.
20 | Evaluation | Plan how to 1) evaluate what ToT trainers have learned and 2) allow both ATs and ComPs to evaluate their own experience. If written, make sure forms are available in advance and included in their information packs, so they can complete after every session. Assess and write up the results, copying all involved, to learn from our experience. |  | Yes No | Find and consider revising formats used in EWS/A.

## Original
| TASK | DESCRIPTION | Who's Responsible | Completed? | NOTES
1 | BUDGET | Confirm budget available and financial flexibility for the training/ workshop | Constant | YES NO
2 | DATE | Select number of days required and exact dates for the training | Constant | YES NO
3 | PARTICIPATION | Make list of all participants including visitors, etc. coming from beyond the region, etc. |  | YES NO | IMPT: refer to advice on selection of EWS Workshop participants
4 | VENUE | Identify availability of appropriate conference type venue and make reservations |  | YES NO | ATTN: confirm adequate availability of electtricity and lighting, and back-up plans
5 | LODGING | Identify availability of appropriate lodging and make reservations for those in need |  | YES NO | Includes hotels in transit (e.g., Freetown) for those coming in on international tickets
6 | INVITATIONS | Make sure all participants are informed (with enough advance notice to procure their visias/tickets, etc.), and confirm their full participation |  | YES NO | Do not forget symbolic government or other "invitees" for opening and closing ceremonies
7 | AGENDA | Prepare a detailed agenda covering all workshop days, clearly identifying who on your team is responsible for each session module |  | YES NO
8 | TECHNICAL CONTENT | Delegate (to each person responsible) the technical agenda content that must be prepared (contextualized to Sierra Leone, etc.) |  | YES NO | This should include the full set of 5-activities for each module (1.intro, 2.energizer(s), 3. new content, 4. application, and 5. testing knowledge of participants)
9 | CERTIFICATES / AWARDS | Decide if you will be giving certificates or awards to anyone, and procure/print/plan for them |  | YES NO
10 | BREAKS/MEALS | Decide what snacks, meals and drinks are needed, and contract company to organize it |  | YES NO
11 | TEAM COMPOSITION | Divide expected participants into appropriate number and composition of teams (For EWS: 1 per key hazard, 1 vulnerability) |  | YES NO | Team composition is very important: this activity requires confirmation of participants, as well as some knowledge of their profiles and personalities
12 | INFORMATION PACKETS | Decide what must be printed and prepared to distribute to participants; plan for its preparation and photocopying, etc. |  | YES NO
13 | MATERIALS and EQUIPMENT | Decide what is needed (e.g., flip charts, markers, photocopy machine, participant notebooks, etc) and plan how to make it available at workshop site |  | YES NO
14 | TRAINING PROPS | Decide what motivational and other training props (maps, signs, balls, noise makers, prizes) are needed to prepare in advance and plan to have them ready |  | YES NO | NB: What about map set for SL? Is this still needed/retained in the agenda for a specific module?
15 | MOTIVATION | Decide the level of excitement you would like to foster in your training, and plan for team competitions, other motivational methods, etc. |  | YES NO | Symbolic amusing prizes may be needed if a competition is planned
16 | FIELD VISIT | Decide if/when you need a site visit in the agenda, clarify objectives and make logistic plans/arrangements for this |  | YES NO
17 | REALITY CHECK | Plan how to touch base regularly with participants with special needs (i.e. semi-literate, etc.) and/or more generally with general participants |  | YES NO
18 | NOTE TAKER | Decide if your training requires notetaking and if so, delegate someone |  | YES NO | Often helps to plan for this on a rotational basis
19 | TIME KEEPER | Decide if your training requires time keeping (most do) and if so, delegate someone |  | YES NO | Often helps to plan for this on a rotational basis
20 | EVALUATION | Plan how to have participants evaluate their experience, if written, make sure it is available in advance and included in their packets |  | YES NO