**TERMS OF REFERENCE**

|  |  |
| --- | --- |
| **TEAM 1 (4 persons)** | **Logistics** |
| Name of participants:  -  -  -  - | Coach  - Handoko  - Eri (warehouse manager) |

|  |
| --- |
| **Objectives**  **1/ Ensure adequate supplies and equipment are provided to the other teams as per the request and schedule**  **2/ Support the food distribution with crowd management and security** |

Preparatory tasks on Thursday 26 May 2016

* Survey the location for the distribution
* Check the available resources in the warehouse
* Collect logistics needs from the 3 other teams
* Prepare an area map
* Prepare list of equipment for the warehouse manager
* Make a plan for the area installation

Friday morning: 08.30-12.30

* Check equipment and supplies
* Supervise the volunteers installing the main tent
* Support the overall installation of the area
* Support ongoing needs from other teams

Distribution: 12.30 – 13.30

* Support management of the people coming to the distribution
* Monitor the distribution site. Are there any restrictions for specific groups to access services? If so, respond to these
* Ensure overall security

**CHECKLIST**

|  |  |
| --- | --- |
| * Is the area map for services accessible (disability, male/female, pregnant women) * Inclusive, queueing / waiting area * Information / signage * Security – is the site itself accessible, equipment safe? | * Prioritization of tasks (ex. Start from the main tent so that team 1 can start cooking as early as possible) * Management of volunteers * Refer to IFRC Minimum Standard Commitments to gender and diversity in Emergency programming! |