Luang Prabang View Hotel

25-27 March  2013, Laos

Follow up on Action points

| Issue | Action /Recommendations | By whom | By when | Next immediate steps | Status |
| --- | --- | --- | --- | --- | --- |
| IFRC to facilitate RM efforts of NS with corporate sector at various levels | Review and analysis of existing successful NS-corporate sector linkages and regional Networks | SEARD, with support of RM APZ | Completed | - APFN Meeting in BKK July 2012 (report) - Coca Cola Meeting & follow up in 2012 - Update on Zurich Insurance - Ongoing mapping of SEA NS partnership with private sector | - All documents posted on SEA Leaders Website - Done |
| Stronger input of SEA NS in Regional Planning | Share detailed plans for regional activities and financial breakdown of regional networking and Training activities | SEARD | During mid term revision of LTPF 2012-2015 | - Share LTPF, Plans and Budget 2014-2015 Revision mechanisms process - Share regional &country plans 2013 - Share Networking and Training analysis (number of workshops, financial costs, etc.) | - All posted on SEA Leaders Website - Done |
| Inclusion of NS issues of concern into revised version of IFRC Principles and Rules of International Disaster Relief | Collection of information from NS to be included in a new version of Principles and Rules of IDR | SEARD /RDMC Process handled by IFRC Secretariat and AP Z DMU | Ongoing process Debriefing on the Gva process at the March Meeting | - Inputs collected from NS in 2012. - Revision of new edition is under way. - Posting of documents on the SEA RCRC Leaders Meeting 2013 Website - Provide input from current discussions at GVA level between Federation and ICRC | - Revised documents posted on SEA Leaders Website - Done |
| Mainstreaming of regional networks (Health, OD, DM) | Review of effectiveness and sustainability of exiting regional networks | SEARD, NS | By end of February 2013 posted on the website | - Mapping of existing regional networks - Share draft ToR (DM, Health and OD) | - Draft ToRs posted on SEA Leaders website - Done |
| Better network cooperation in times of disasters | More engagement between the RDMC with ASEAN Committee of DM | RDMC Chair | ongoing | - Increased participation in ASEAN meeting - Stronger dialogue with ASEAN Secretariat and AHA Centre (invitation of Director AHA Centre in RDMC Meeting, June 2012) | - Done - Achieved |
| ICRC and NS collaboration on regional level | Include a session on ICRC – NS mechanism and issues in the agenda of next Meeting, including a question of setting up a working group | PMI, ICRC | By 1st march 2013 | - Session included in 2013 agenda | - Done |
| ToR of the meeting: Meeting title and numbering | To update Meeting title as follows: (number) Annual South-East Asia Leaders Meeting (year) | SEARD | By end of February 2012 | - Meeting number ant title updated | - Done |
| ASEAN Cooperation Framework | To draft a letter to the ASEAN SG regarding the proposed ASEAN Cooperation Framework | Singapore RC, SEARD HoD | Ongoing | - Letter completed and shared with ASEAN Secretariat in September 2012 together with the Cooperation Framework draft 6 - Meeting held with ASEAN Secretariat in Yogyakarta with ASEAN Secretariat Head of DM (Adelina Kamal) - Participation to 21st ACDM session in January 2013, Cooperation Framework discussed with ACDM Members. Recommendations made before submitting the current draft to ASEAN Permanent States Members - Invitation of ASEAN Secretariat Head of DM and Director of AHA Centre at SEARD Bangkok to discuss current areas of cooperation | - Documents on ASEAN-IFRC cooperation posted on SEA Leaders website - All mentioned Meetings held - Done |
| NS Staff development | To enable NS key staff to be seconded to IFRC/ICRC | SEARD | By end of February 2013 | - To present IMPACT calendar for 2013 - Briefing on Learning Platform/IFRC Job Net - Staff on Loan position, Financial support for SEA NS delegates | - Documents posted on SEA Leaders website - Done |
| Calendar of Regional events/activities | To improve planning and participation of NS to events | SEARD / ICRC | By end of February 2013 | - To share, present and review the calendar and get input from NS - SEARD List of event Matrix | - Documents posted on SEA Leaders website - Done |