10th Annual South-East Asia Red Cross Red Crescent Leaders Meeting 2013

OD and Youth Working Group

South-East Asia Leaders /Luang Prabang / 25 – 27 March 2013

Framework for strengthening NS

Organisational Capacity Assessment Certification (OCAC)

- In 2012 Myanmar first SEA NS to pilot OCAC. Self assessment finalized and Myanmar RC evaluating next steps to support identified weaknesses.

- PRC, VNRC and CVTL have indicated interest in OCAC / this needs follow-up and confirmation with Geneva Team.

- Currently no SEA countries on GVA list for 2013 OCAC round .

- CRC and PMI want to wait and observe.

Fed-wide Databank & Reporting

- Slow progress in this area due to: poor internet connection (CVTL); need for more clarification (Myanmar RC); challenge of data collection (PMI); activity delayed while HR system gets ready (VNRC).

Learning and Knowledge Sharing Network

- 8,305 users from Asia Pacific and 30,880 users globally

- AP is 60% of population, but only 26% of users from APZ

- Need to facilitate more usage which requires local language and better connectivity

Digital Divide

- Steady progress by Myanmar RC, CRC, CVTL, PRC and VNRC

- Support provided by Singapore RC to Myanmar RC

- VNRC noted their good progress was based on strong commitment from Leadership

Volunteer Development

- 30% coverage of 2 million Volunteers in SEA: TRC & CVTL have 100% coverage; SRC & PRC, volunteers have “own insurance”; CRC (9%), PMI (>1%), Malaysia RC (42%) and Myanmar RC (6%); BRC, LRC and VNRC (0%).

- Recent development with Zurich Insuarnce partnership (PMI)

- Consider targeted support for countries under 10% coverage.

Youth Development / Networks

- Youth Policies:  strong coverage - nearly 100%

  - Yes:  CVTL, PMI, Myanmar RC, PRC, TRC & VNRC

  - Drafting/Reviewing:  BRC, CRC, Malaysia RC, SRC

  - No:  LRC

- Youth in Governance/decision making:  good progress – over 50% coverage

  - Yes:  CRC, CVTL, Malaysia RC, Myanmar RC, PRC, TRC

  - No:  BRC, PMI, LRC, SRC, VNRC

- Youth & OD Forum merged for greater impact & sustainability (next forum mid May)

- Youth networking, 2nd  Model IFRC General Assembly (MIGA) meeting in Korea. AP and SEA NS invited to attend in August 2013.

Resource Mobilization(RM)

- 8 of 11 NSs are making good progress in RM

- LRC has requested support from Region

- BRC & Malaysia RC have not indicated progress in RM

- Good to look into twinning NSs with strong RM to NSs needing support

Resource management Systems (RMS)

- PRC and CVTL  lead the way in RMS

  - PRC has trained 78 chapter, and chapters now doing data entry on Volunteers

  - CVTL has implemented in 6 branches (but trouble with updating off-line

  - Good for PRC & CVTL to share implementation experience

Finance Development

- PRC has implemented Navision software and is now using it; reviewed accounting policies and procedures and developed new finance manual

- Myanmar RC has started implementation of Navision software

- VNRC completed first ever consolidated audit of VNRC financial statement

- Important to ensure smooth link between Fin Dev similar area in OCAC

Planning, Monitoring, Evaluation and Reporting (PMER)

- PMI started 3 year PMER project. 1 American RC staff embedded in PMI Planning bureau

- CVTL 2012 planning included branches, and is receiving PMER training from Zone

- VNRC is standardizing PMER training with pilot trainings in targeted branches

- LRC began review process in late 2012 with SEARD support

- Capacity building initiative  is in progress in Myanmar RC

HR

- PMI recruited experienced HR manager feeling it will be better than workshops

- Myanmar RC is experiencing turn over of experienced staff in a country fast changing environment.

- CVTL recruited HR/Admin manager, and also struggled with high turn-over in 2012

- VNRC drafted ToR on HR change management for HQ, consultant to be engaged; but without OD focal point challenging to facilitate process

- Must ensure management commitment to HR  process or any effort will be useless

- May be useful to review HR remuneration package to remain competitive

- Consider case study on success of PMI and CVTL HR manager approach

Legal Base  (5 NS up to date; 5 NS under review/revision; 1 NS in planning process)

- VNRC revised statutes approved in Dec 2012

- PMI drafted Red Cross Law in 2012

- Myanmar RC showns good progress in the revision  of Myanmar  RCS Act to the Attorney General’s Office

- CVTL plans to review its 10 yr old Constitution. Draft Law & Constitution completed

- Malaysia RC revised statutes awaiting governance approval

- LRC has submitted Legal Base (2010) revision to Government for review

- BRC planning constitutional review

Strategic Planning

- 10  NSs have updated strategic plans or are in various stages of updating

- BRC  draft Strategic Plan prepared and  under review by Executive Committee (Top Priority)

Branch Development

- CRC, LRC engaged in decentralization/categorization process of  it branches in 2012.

- New CRC OD integrated MODEL Has been developed ,  presented to RCRC partners and will be piloted.

- CVTL has active Branch Dev programme to develop Branch Coords skills in planning, budgeting and communications

- PRC trained 8 facilitators how to facilitate Chapter Development Game

- Encourage discussions with NSs on:

  - Categorization process

  - Skills training of branch managers

  - Success Branch Development Game

# Regional contact information: Head of regional national society development unit: Nina Nobel: nina.nobel@ifrc.org