Luang Prabang View Hotel

25-27 March 2013, Laos

**Follow up on Action points**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Issue | Action /Recommendations | By whom | By when | Next immediate steps | Status |
| IFRC to facilitate RM efforts of NS with corporate sector at various levels | Review and analysis of existing successful NS-corporate sector linkages and regional Networks | SEARD, with support of RM APZ | Completed | * APFN Meeting in BKK July 2012 (report)
* Coca Cola Meeting & follow up in 2012
* Update on Zurich Insurance
* Ongoing mapping of SEA NS partnership with private sector
 | * All documents posted on SEA Leaders Website
* **Done**
 |
| Stronger input of SEA NS in Regional Planning  | Share detailed plans for regional activities and financial breakdown of regional networking and Training activities | SEARD | During mid term revision of LTPF 2012-2015 | * Share LTPF, Plans and Budget 2014-2015 Revision mechanisms process
* Share regional &country plans 2013
* Share Networking and Training analysis (number of workshops, financial costs, etc.)
 | * All posted on SEA Leaders Website
* **Done**
 |
| Inclusion of NS issues of concern into revised version of IFRC Principles and Rules of International Disaster Relief | Collection of information from NS to be included in a new version of Principles and Rules of IDR | SEARD /RDMCProcess handled by IFRC Secretariat and AP Z DMU | Ongoing process Debriefing on the Gva process at the March Meeting | * Inputs collected from NS in 2012.
* Revision of new edition is under way.
* Posting of documents on the SEA RCRC Leaders Meeting 2013 Website
* Provide input from current discussions at GVA level between Federation and ICRC
 | * Revised documents posted on SEA Leaders Website
* **Done**
 |
| Mainstreaming of regional networks (Health, OD, DM) | Review of effectiveness and sustainability of exiting regional networks | SEARD, NS | By end of February 2013 posted on the website  | * Mapping of existing regional networks
* Share draft ToR (DM, Health and OD)
 | * Draft ToRs posted on SEA Leaders website
* **Done**
 |
| Better network cooperation in times of disasters  | More engagement between the RDMC with ASEAN Committee of DM | RDMC Chair | ongoing | * Increased participation in ASEAN meeting
* Stronger dialogue with ASEAN Secretariat and AHA Centre (invitation of Director AHA Centre in RDMC Meeting, June 2012)
 | * **Done**
* **Achieved**
 |
| ICRC and NS collaboration on regional level | Include a session on ICRC – NS mechanism and issues in the agenda of next Meeting, including a question of setting up a working group | PMI, ICRC | By 1st march 2013 | * Session included in 2013 agenda
 | * **Done**
 |
| ToR of the meeting: Meeting title and numbering | To update Meeting title as follows: (number) Annual South-East Asia Leaders Meeting (year) | SEARD | By end of February 2012 | * Meeting number ant title updated
 | * **Done**
 |
| ASEAN Cooperation Framework  | To draft a letter to the ASEAN SG regarding the proposed ASEAN Cooperation Framework  | Singapore RC, SEARD HoD | Ongoing  | * Letter completed and shared with ASEAN Secretariat in September 2012 together with the Cooperation Framework draft 6
* Meeting held with ASEAN Secretariat in Yogyakarta with ASEAN Secretariat Head of DM (Adelina Kamal)
* Participation to 21st ACDM session in January 2013, Cooperation Framework discussed with ACDM Members. Recommendations made before submitting the current draft to ASEAN Permanent States Members
* Invitation of ASEAN Secretariat Head of DM and Director of AHA Centre at SEARD Bangkok to discuss current areas of cooperation
 | * Documents on ASEAN-IFRC cooperation posted on SEA Leaders website
* All mentioned Meetings held
* **Done**
 |
| NS Staff development  | To enable NS key staff to be seconded to IFRC/ICRC  | SEARD | By end of February 2013 | * To present IMPACT calendar for 2013
* Briefing on Learning Platform/IFRC Job Net
* Staff on Loan position, Financial support for SEA NS delegates
 | * Documents posted on SEA Leaders website
* **Done**
 |
| Calendar of Regional events/activities | To improve planning and participation of NS to events | SEARD / ICRC  | By end of February 2013 | * To share, present and review the calendar and get input from NS
* SEARD List of event Matrix
 | * Documents posted on SEA Leaders website
* **Done**
 |