International Federation of Red Cross and Red Crescent Societies

Beneficiary communications in Southeast Asia: overview of achievements

IFRC South-East Asia regional delegation / Bangkok / Sept 2012 - March 2013

# Background

The following is a brief overview on the achievements and ongoing work of the beneficary communications delegate in the IFRC regional delegation for South-East Asia.

# Advocacy  and external relations

- Production/printing of BC infographic

- Production of case study for PMI on beneficiary communciations during earthquake in 2012

- Movement wide case on BC in the Philippines

- Baseline activities regionally: https://ifrcbcsoutheastasia.crowdmap.com/

- Blog piece Reuters Alert net

- Finalisation of BC animation.  Translation will happen in 5 languages (French, Spanish, Burmese, Vietnamse, Sri Lankan)

- Contributions to AP voices, ifrc.org and the IFRC beneficiary communications newsletter

# Integration and fundraising

- Workshop with Health Leaders across the region on BC and integration into programming

- Follow up from that workshop with Health leaders with materials to integrate BC within programmes

- Workshop with National Society leaders (Migration workshop) on the use of technology, beneficiary communications

- Integration in two proposals (HK RC proposal and Soonyoung proposal) BC activities and concepts.  Awaiting confirmation of funding.

- Working with Zone colleagues on feedback on Manual for BC.

- Presentation to ASEAN on TERA and UN early preparedness representatives from WFP on TERA and BC.

- BC simulation at APZ communications forums

National Societies and TERA

## Viet Nam RC

- Working with Amcross regionally to develop proposal for funding disaster App.

- Developing a BC plan with VNRC

- Rollout of TERA in Vietnam under the VFD project

- Two field visit to Viet Nam

  - First visit to the NS and meeting with Kendall, American RC representative who is funding the roll out of TERA. Main purpose was outlining the work plan for 2013 and planning a workshop with the funding consortium, WinROCK, which is taking place in March.

  - Workshop with National Society and partners on VFD project on BC

  - Planning for BC within National society and development of BC plan for NS

  - TERA concept note for rollout in Vietnam

  - Attend at VNRC and consortium partners retreat for 3 days.

  - Socialisation of TERA and BC within National society, PNS and to consortium partners

## Indonesian RC

- Radio workshop proposed and in development with PMI and PRC

## Philippine RC

- Development of POA section for BC for Cyclone Bopha

- Provision of technical support to PRC health team in drafting information assessment for recovery phase of Bopha operations

- Field visit to Philippines to document BC activities

  - Case study, photo montage and blog piece are produced in February

  - Meetings with Secretary General of PRC and UNOCHA to discuss points of collaboration with ongoing UN activities

  - Interview with IFRC/PRC management for baseline assessment and identification of needs for support on integration of BC into health activities

  - Discussions on TERA and proposed plan for technical training

## Thai RC

- Development of BC concept note for Thai Red Cross

- Discussions with Thai RC on use of TERA and other beneficiary communications materials for relief pacakages

## Myanmar RC

- Development of an information survey for Rakine with BC delegate on the ground

- Potential workshop for beneficiary communication in quarter 2

- Ongoing support for the IFRC communications delegate

# How we work

Strategy 2020 voices the collective determination of the International Federation of Red Cross and Red Crescent Societies (IFRC) to move forward in tackling the major challenges that confront humanity in the next decade. Informed by the needs and vulnerabilities of the diverse communities with whom we work, as well as the basic rights and freedoms to which all are entitled, this strategy seeks to benefit all who look to Red Cross Red Crescent to help to build a more humane, dignified, and peaceful world.