## Activity plan 2013-2014
South East Asia Youth Network Activity Plan 2013-2014 (Final)
Goal: “To Enhance NS service delivery by mobilizing resources of youth in the region and by developing the regional youth action in the aspiration for positive change"
ACTIVITIES | 2013 | [6 empty] | 2014 | [11 empty] | Hosting Members | CT Responsibility
Outcomes: SEA NSs are more effective and efficient in service delivery to targeted communities thru Youth interventions | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Activities 1: Establish the SEA Youth Network and working system
1.1 Complete SEA Youth Network Terms of Reference, coordination team roles and responsibilities. | [19 empty] | All members | All/IFRC | bar: 2013 Jun
1.2 Nominate SEA Youth Network members (NS youth staff and youth leaders) and circulate to all NSs in the name of SEAYN Chair | [19 empty] | All members | Chair, IFRC | bar: 2013 Jun to 2013 Jul
1.3 Develop the youth network activities 2013-2014 | [19 empty] | All members | All/IFRC | bar: 2013 Jul
1.4 Introduce the SEA Youth network activities to NS leadership and SEA Youth community | [19 empty] | All members | All/IFRC | bar: 2013 Jul to 2013 Aug
1.5 Hold SEA Youth Network Coordination Team online Meeting and face to face meeting | 2013 Jul: X; 2013 Sep: X; 2013 Nov: X TBC; 2014 Jan: X; 2014 Mar: X; 2014 May: X; 2014 Jul: X; 2014 Sep: X; 2014 Nov: X | All members | All/IFRC
1.6 Hold SEA Youth Network online meetings and annual meeting | 2013 Jul: X; 2013 Sep: X; 2013 Nov: X; 2014 Jan: X; 2014 Mar: X; 2014 May: X TBC; 2014 Jul: X; 2014 Sep: X; 2014 Nov: X | All members | All/IFRC
Activity 2: Five-Priortised Network Activities implemented
2.1 Improve Youth strategy, Youth Policy of SEA NSs | [19 empty] | CRC, LRC, MalRC??(TBC) | Dep chair and officer/IFRC | bar: 2013 Aug to 2014 Dec
2.2 Develop National Youth Network in schools and universities and elect youth leaders (volunteers) and conduct RC orientation trainings for them | [19 empty] | LRC, TRC??(TBC) | Dep chair and officer/IFRC | bar: 2013 Aug to 2014 Dec
2.3 Develop School Red Cross youth training in integration with school curriculum,and the ICBDRR projects and healthy youth training, culture of sharing | [19 empty] | CVTL(TBC) | Dep chair and officer/IFRC | bar: 2013 Aug to 2014 Dec
2.4 Develop pilot regional youth project to community service and raise the funds | 2013 Jun: Pls see the Activity 3 below. |  | All/IFRC
2.5 Update and share SEA NS youth development (statistics and information) and keep informed of global youth development | [19 empty] | All members | Chair /IFRC | bar: 2013 Sep; 2013 Nov; 2014 Jan; 2014 Mar; 2014 May; 2014 Jul; 2014 Sep; 2014 Nov
Activity 3: Regional Youth Project to Community Service Programme Proposal developed and implemented
3.1 Develop youth questionare to identify what youth needs and can do in the communities and send to NS youth dept through network | [19 empty] | All members | All/IFRC | bar: 2013 Jul to 2013 Aug
3.2 Analyse the questionare and select pilot 2-3 NSs which have interest for Regional Youth project | [19 empty] | selected members | All/IFRC | bar: 2013 Aug
3.3 Regional youth project Proposal for selected NSs drafted and approved | [19 empty] | selected members | All/IFRC | bar: 2013 Aug to 2013 Sep
3.4 Regional Youth Project Proposal sent to PNSs or private sectors | [19 empty] | selected members | IFRC | bar: 2013 Sep to 2013 Nov
3.5 Funds raised and regional Youth Project started implementation and monitored (TBC) | [19 empty] | selected members | All/IFRC | bar: 2014 May to 2014 Dec
Remarks: This SEAYN action plan was finalised based on SEA NS youth plan 2013-2014 during first Network Online meeting held in July 2, 2013. This plan considered the preliminary plan (attached)issued from OD and Youth forum held in May 2013 and IFRC Regional Development Operation Plan 2013-2014 as well. TBC: To Be Confirmed

## shortcut
South East Asia Youth Network Activity Plan 2013-2014 (Final)
Goal: “To Enhance NS service delivery by mobilizing resources of youth in the region and by developing the regional youth action in the aspiration for positive change"
ACTIVITIES | CT Responsibility | Hosting Members | 2013 | [6 empty] | 2014
Outcomes: SEA NSs are more effective and efficient in service delivery to targeted communities thru Youth interventions |  |  | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Activities 1: Establish the SEA Youth Network and working system
1.1 Complete SEA Youth Network Terms of Reference, coordination team roles and responsibilities. | All/IFRC | All members | bar: 2013 Jun
1.2 Nominate SEA Youth Network members (NS youth staff and youth leaders) and circulate to all NSs in the name of SEAYN Chair | Chair, IFRC | All members | bar: 2013 Jun to 2013 Jul
1.3 Develop the youth network activities 2013-2014 | All/IFRC | All members | bar: 2013 Jul
1.4 Introduce the SEA Youth network activities to NS leadership and SEA Youth community | All/IFRC | All members | bar: 2013 Jul to 2013 Aug
1.5 Hold SEA Youth Network Coordination Team online Meeting and face to face meeting | All/IFRC | All members | 2013 Jul: X; 2013 Sep: X; 2013 Nov: X TBC; 2014 Jan: X; 2014 Mar: X; 2014 May: X; 2014 Jul: X; 2014 Sep: X; 2014 Nov: X
1.6 Hold SEA Youth Network online meetings and annual meeting | All/IFRC | All members | 2013 Jul: X; 2013 Sep: X; 2013 Nov: X; 2014 Jan: X; 2014 Mar: X; 2014 May: X TBC; 2014 Jul: X; 2014 Sep: X; 2014 Nov: X
Activity 2: Five-Priortised Network Activities implemented
2.1 Improve Youth strategy, Youth Policy of SEA NSs | Dep chair and officer/IFRC | CRC, LRC, MalRC??(TBC) | bar: 2013 Aug to 2014 Dec
2.2 Develop National Youth Network in schools and universities and elect youth leaders (volunteers) and conduct RC orientation trainings for them | Dep chair and officer/IFRC | LRC, TRC??(TBC) | bar: 2013 Aug to 2014 Dec
2.3 Develop School Red Cross youth training in integration with school curriculum,and the ICBDRR projects and healthy youth training, culture of sharing | Dep chair and officer/IFRC | CVTL(TBC) | bar: 2013 Aug to 2014 Dec
2.4 Develop pilot regional youth project to community service and raise the funds | All/IFRC |  | 2013 Jun: Pls see the Activity 3 below.
2.5 Update and share SEA NS youth development (statistics and information) and keep informed of global youth development | Chair /IFRC | All members | bar: 2013 Sep; 2013 Nov; 2014 Jan; 2014 Mar; 2014 May; 2014 Jul; 2014 Sep; 2014 Nov
Activity 3: Regional Youth Project to Community Service Programme Proposal developed and implemented
3.1 Develop youth questionare to identify what youth needs and can do in the communities and send to NS youth dept through network | All/IFRC | All members | bar: 2013 Jul to 2013 Aug
3.2 Analyse the questionare and select pilot 2-3 NSs which have interest for Regional Youth project | All/IFRC | selected members | bar: 2013 Aug
3.3 Regional youth project Proposal for selected NSs drafted and approved | All/IFRC | selected members | bar: 2013 Aug to 2013 Sep
3.4 Regional Youth Project Proposal sent to PNSs or private sectors | IFRC | selected members | bar: 2013 Sep to 2013 Nov
3.5 Funds raised and regional Youth Project started implementation and monitored (TBC) | All/IFRC | selected members | bar: 2014 May to 2014 Dec
Remarks: This SEAYN action plan was finalised based on SEA NS youth plan 2013-2014 during first Network Online meeting held in July 2, 2013. This plan considered the preliminary plan (attached)issued from OD and Youth forum held in May 2013 and IFRC Regional Development Operation Plan 2013-2014 as well. TBC: To Be Confirmed