**WORKPLAN Template for 2017**

**Component**: Disaster Law

**Lead:** Gabrielle Emery, Asia Pacific Disaster Law Programme Coordinator

**Intermediate outcome 1100:** Improved representation of community Disaster Risk Reduction (DRR) issues [2] in national policies, plans, and programs.

**Immediate outcome 1110:** Increased capacity of SEA Red Cross National Societies (hereafter referred to as NSs) to promote community DRR issues at national level

**Output 1113:** Technical support provided to select NSs to develop Disaster Law advocacy plans & processes.

**REGIONAL ACTIVITIES**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity Name | Description | Tentative date | Estimated budget | Focal person in IFRC |
| RRI Country and ASEAN Participation Asia Pacific disaster law ‘Field School ‘ | 3 RRI countries (Myanmar, Laos and Indonesia) and CRC Legal and CRC DM domestic have been identified for participation in the Disaster Law Field School to be held in Sydney, Australia from 24 – 27 April 2017. Country delegations will comprise of representatives from National Societies and NDMOs. Representatives from ASEAN and AHA will also be invited to attend. In total, there will be 12 participants funded from the RRI to attend.  | 24 – 27 April 2017 | 20,000 CHF for SEA participants8.000 CAD for Canadian RC participants | Gabrielle Emery/ Julia Hartelius |
| Disaster Law Case Studies/ Change Stories and Communication | capture Disaster Law Case Studies and Change Stories over 2017. Case studies can be presented through multimedia, including written form, sound clip to video. Case Studies will be included in the DL and RRI newsletters, web stories. Regional Snapshot for DL in ASEAN will be produced to support interventions in key ACDM meetings (April, October). Following on the learnings from the Disaster Law Field School, representatives will participate in an IDL workshop in Canada to coincide with the Canadian Risk & Hazards Network and Canada’s Platform for Disaster Risk Reduction National Roundtable in Halifax the week of October 23.  | Ongoing until Dec 2017. Monthly RRI newsletter, quarterly AP DL Newsletter Snapshot – April/ October | 5,000 CHF | Gabrielle Emery/ Julia Hartelius  |
| Printing and translation of disaster law materials  | Printing and translation of disaster law tools (e.g. IDRL Guidelines, DRR checklist, snapshot etc.) takes place throughout the year, to ensure we have adequate supplies to distribute during workshops, regional and national events, briefings with partners etc.  | Ongoing until Dec 2017, as necessary. | 5,000 CHF | Gabrielle Emery/Padmini Nayagam |
| Disaster law Team travel  | To cover country level disaster law missions, as well as travel to support other initiatives that may arise (ACE, civ -mil, relevant ASEAN meetings) | Ongoing until Dec 2017, as necessary | 16,000 CHF | Gabrielle Emery/Pauline Caspellin Arce/ Julia Hartelius |
| ASEAN Disaster Law Mapping  | The ACDM recently approved IFRC to undertake a regional disaster law mapping for ASEAN countries. The mapping will consolidate past disaster law initiatives across South East Asia (IDRL and DRR and Law, HLP), as well as an analysis of relevant national laws against domestic disaster preparedness and response (TOR). Regional Mapping will also include one consultation workshop to verify initial research findings | April – October 2017 | 50,000 CHF | Gabrielle Emery /Pauline Caspellin Arce |
| ASEAN Disaster Law and Policy Platform  |  An ASEAN DL and Policy Platform will be piloted in 2017 to facilitate shared learning and dialogue b/w ASEAN member states on approaches to disaster risk governance. For 2017, the first peer platform will be held in Lao and invite participation from 2 other ASEAN members |  June/ July 2017 | 10,000 CHF | Gabrielle Emery /Pauline Caspellin Arce |

**IN-COUNTRY ACTIVITIES**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Country | Activity Name | Description | Tentative date | Estimated budget | Focal person in NS | Notes |
| LAO PDR |  |  |  |  |  | **Gabrielle Emery /Pauline Caspellin Arce** |
|  | National and Provincial Disaster Law Consultations  | IFRC will support two provincial level consultations on draft DRM / CC Law for Laos and one Stakeholder Consultation (national level) to support consultation, and feedback into draft law | March – June 2017 | 15,000 CHF | Mr. Thongphachanh Sonnasinh | 2 provincial consultations; 1 national stakeholder consultation, as well as mission costs |
| CAMBODIA |  |  |  |  |  | **Julia Hartelius/Gabrielle Emery** |
|  | Provincial level Disaster Law Dissemination  | Following on from the National Disaster Law Dissemination, including development of speaker’s kit (January 2017), three provincial level disseminations will be held in 2017, using speakers kit methodology and IEC materials developed | March/ April 2017 | *\*12,000 CHF (rollover from 2016)* | Dr. Sam Ath and Dr. Sam Onn | Budget to cover three workshop and travel costs for convening of provincial DL disseminations) |
|  | UNDP/ IFRC DRR and Law Subsidiary Legislation Report Launch  | Subsidiary legislation report has been finalised internally and awaiting feedback from Govt of Cambodia. IFRC to cover layout and printing of report and UNDP to cover launch/handover report | March – June 2017  | 5,000 CHF | Gabrielle Emery  | Report lay out and publication and mission to support report launch. |
| VIETNAM |  |  |  |  |  | **Julia Hartelius** |
|  | Know Your Rights, Roles and Responsibilities (3Rs) in Disasters [ modules development and ToT] | Know your 3 Rs in Disasters – a module to raise awareness of DRM framework, and rights roles and responsibilities therein. Aim to strengthen community participation in DRM decision making as well as more connected local/ national policy making. This activity will include development of a dissemination module and **national level ToT** for 24 VNRC staff/ volunteers and **one provincial ToT** | From June | 12,000 CHF | Dr Hung |  |
|  | “know your rights” IEC materials and community engagement activities  | Development of relevant messaging and IEC materials on “know your 3Rs in disasters” to use in training and dissemination activities – including Comic books, calendars, TVC, school competitions, social media on DL | By May 2017 | 5,000 CHF + another 5,000 CHF (TBC) | Dr. Hung | IEC materials and messages, as well as dissemination through appropriate communication channels. |
|  | Two regional disaster law workshops and one provincial level “Know your Rights” | DM Law dissemination workshops in Central and Southern Vietnam. Target audience, local authorities, CSO and communities | After June  | 20,000 CHF  | Dr Hung | Training costs and facilitation |
|  | Adaption of Sphere Handbook and Messaging for Vietnam  | VNRC to lead in awareness dissemination on humanitarian values and principles for local organisations etc through development of easy to use tools adapted for Vietnam  | May – November 2017 | 10,000 CHF  | Dr. Hung | Production and printing |
| INDONESIA |  |  |  |  |  | **Pauline Caspellin Arce** |
|  | DRR and Law Research and Dissemination | Follow on from 2016 Launch of DRR and Law Report for Indonesia. To produce Indonesia language version of full report and printing, as well as small advocacy flier for use in dissemination / advocacy efforts | April – May 2017 | 5,000 CHF | Pak Arifin | production, printing and translation costs of report, and advocacy flier  |
| MALAYSIA |  |  |  |  |  | **Gabrielle Emery** |
|  | National Level Sensitisation Workshop on Disaster law  | National level sensitisation workshop in partnership with MRCS/ Malaysia IHL Committee on global/ regional DRM policy agendas in DRM as well as national level implementation in Malaysia through law and policy frameworks. To invite government and key development and humanitarian partners | October 2017 (TBC) | (10,000 CHF - TBC) | Mr. Saiful Izan Bin Nordin | Training costs and facilitation as well as development of suitable IEC material |
| MYANMAR |  |  |  |  |  | **Gabrielle Emery** |
|  | IDRL research report launch and phase II roadmap | Finalise IDRL Research Report for Myanmar and Small Launch Event with key stakeholdersDevelop and agree on roadmap for phase II implementation of recommendations | May 2017  | 10,000 CHF | San San Maw | Layout, printing of full report in English and Myanmar Language, small launch event and road map discussions |
|  | DRM Legislative Advocacy Plan | Discussions on DMR Law Advocacy Planning (MRCS – to incorporate, AMCDRR follow up and future DL work, finalise contribution to Myanmar DRM Handbook) | April – November 2017 | 5,000 CHF | San San Maw |  Facilitate development and implementation of advocacy plan on key DRM law issues  |
| PHILIPPINES  |  |  |  |  |  | **Pauline Caspellin Arce** |
|  | DL Trainings – chapter and national govt | Development and implementation of specialized trainings for NS Chapter staff and volunteers on key DL themes and legislative advocacy | June & August 2017 | 4,200 CHF | Resty Lou Talamayan / Ana Mariquina | Expenses for 2 workshops, mission expenses |
|  | DL peer-to-peer exchange  | A peer-to-peer exchange for Philippines (Govt and NS )to explore enabling frameworks for disaster recovery and build back better ( potential exchange partners identified as either New Zealand or Indonesia ) | November 2017 | (10,000 CHF -TBC) | Resty Lou Talamayan / Ana Mariquina | Participants’ travel and accommodation expenses, workshop expenses |
|  | DL PRC Technical Working Group (TWG) meetings (internal) | TWG meetings to support NS and partners in discussing DL issues and positioning. This will include TWG meetings on the Sunset Review & drafting of the NS Housing, Land and Property (HLP) Advocacy and Mitigation Strategy.  | April – November 2017 | 5,000 CHF | Resty Lou Talamayan / Ana Mariquina / Mauro Victorio | Expenses for 6 TWG meetings & 1 workshop on the HLP Strategy; field/mission expenses  |
|  | Ongoing technical support to NS, govt | Technical/research and financial support for the passage of the DRRM Act amendatory bill at executive and legislative branches | Ongoing until Dec 2017/ As necessary | 4,000 CHF | Resty Lou Talamayan / Ana Mariquina | Meeting and writ-eshop expenses |
|  | PRC Disaster Law Talk at university | Roundtable discussion between DL practitioners and university students (preferably law students) | November | 1,600 CHF | Resty Lou Talamayan / Ana Mariquina | Workshop expenses |
|  | “Know Your Rights” IEC materials and community engagement activities | 2 Know Your Rights in DL IEC publications – 1 for NS chapter level, 1 for national level stakeholders, including dissemination workshop | September & October | 5,000 CHF | Resty Lou Talamayan / Ana Mariquina | Publication and dissemination expenses |
| TIMOR LESTE | Advocacy planning (TBC) | *No activities for Timor Leste planned for first half of 2017 on advice from Indonesia CCST [ to review after national elections to see if opportunity for engagement]*After the elections, potential preparation of an advocacy plan for the promotion of draft Disaster Response Law and the auxiliary role of the Red Cross for the new Government. | November 2017 | 2,000 CHF (TBC) | TBC | Expenses for meetings with government, translation of current draft of the law in Tetum, advocacy materials printing, etc. |
| THAILAND |  |  |  |  |  | **Gabrielle Emery** |
|  | Awareness/ Dissemination of International Assistance Guideline | To support an awareness/ dissemination event on new national international assistance guideline [ developed by DDPM and MOFA end of 2016] |  | (5,000CHF -TBC) | Dr. Amnat Barlee, Khun Arun and Khun Aimee from DDPM | This activity still needs to be discussed with DDPM and TRC and confirm whether or not they wish to go ahead. |