**TERMS OF REFERENCE**

|  |  |
| --- | --- |
| **TEAM 2 (4 persons)** | **Water and Sanitation** |
| Name of participants:- Sophita Thanyalakmetha- Henrikus Adi Hernanto- Phlang Ponleu Rath - Hong Quyen Pham  | Coach- Ridwan (PMI HQ) |

|  |
| --- |
| **Objectives****1/ Provide clean water for 500 community members, both those involved in the simulation exercise and those living in surrounding areas****2/ Ensure the availability of toilet and hand-washing facilities for all participants of the simulation** |

Preparatory tasks on Wednesday 11 October

* Check the available facility and vehicles (water truck)
* Role repartition within the team
* Schedule and itinerary for water trucking (distribution plan)
* Location of hand-washing facility in the main field

Thursday morning: 08.30-12.00

* Installation of hand washing facility
* Water trucking in the village
* Installation of signage / security signs to the toilets

**CHECKLIST**

|  |  |
| --- | --- |
| * Is there safe access for toilets (for all components of the population)
* Separate toilets for men / women?
* Disability access
* Information / signage
 | * Adequate size and volume of water?
* Can toilet be locked?
* Enough light for toilet?
* Antiseptic available for hand washing?
* Preventive message about SGBV?
 |