TERMS OF REFERENCE

| TEAM 5 (4 persons) | Field Coordination |
| --- | --- |
| Name of participants: - Muhammad Azhar Said - Ferosa Arsadita - Toung Kimtol - Jittaporn Wilaijit | Coach: Anne (PMI) |

Objectives 1/ Ensure effective coordination among the three other teams based on their respective objective, including through the establishment of a field command post in the location of the operation 2/ Ensure appropriate representation and coordination with external stakeholders (media, donors, local authorities, traditional leaders, etc.) 3/ Design a system to welcome people, register individually and identify their specific needs - and refer then to specific activities below based on needs 4/ Be responsible for the RFL services in the operation

Preparatory tasks on Wednesday 11 October

- Coordinate the preparation of the four other teams

- Prepare a press release (with focus on inclusion)

- Hold a coordination meeting to validate all plans.

- Design necessary assessment forms, registration forms and vouchers

- Hold a meeting with the Demak Regent and his team as well as traditional leaders at 20.00 hrs to brief them on the operation

Thursday 12

- Ensure overall coordination among the four other teams

- Set up the field command post as the information centre for the operation

- Participate in meetings with district authorities when required

- Handle media, donors and local authorities as needed

- Welcome people arriving at the registration desk

- Register and assess needs, provide vouchers for food distribution

- Based on needs handle specific cases and refer to related activities or services

- Organize the RFL desk

CHECKLIST

| - Principles and rules for Humanitarian Assistance - SPHERE Standards - Information sharing among teams - Refer to IFRC Minimum Standard Commitments to gender and diversity in Emergency programming! | - Time management - Menus, site map, distribution services, registration – check inclusiveness. Are any groups being left behind? - Nominate team leaders? |
| --- | --- |