| LOGICAL FRAMEWORK TEMPLATE |  |
| --- | --- |

Click the links for definition of terms, example logframe 1 and example 2 and project/programme planning guidance manual on Fednet

| [Project Name] LOGFRAME |
| --- |
| OBJECTIVES | INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| Goal |  |  |  |
| Outcome 1 |  |  |  |
| Output 1.1 |  |  |  |
| Output 1.2 |  |  |  |
| Output 1.3 |  |  |  |
| Activities Activities may often be included in separate document (activity schedule) for practical purposes | Inputs/resources | Costs & sources |  |
| Outcome 2 |  |  |  |
| Output 2.1 |  |  |  |
| Output 2.2 |  |  |  |
| Output 2.3 |  |  |  |
| Activities | Inputs/resources | Costs & sources |  |
| Outcome 3 |  |  |  |
| Output 3.1 |  |  |  |
| Output 3.2 |  |  |  |
| Output 3.3 |  |  |  |
| Activities | Inputs/resources | Costs & sources |  |
| Continue to add additional rows for outcomes, outputs and activities as necessary |

| IFRC Logical Framework (logframe) – Definition of Terms |
| --- |
| OBJECTIVES (What we want to achieve) | INDICATORS (How to measure change) | MEANS OF VERIFICATION (Where / how to get information) | ASSUMPTIONS (What else to be aware of) |
| Goal The long-term results that an intervention seeks to achieve, which may be contributed to by factors outside the intervention. | Impact Indicators Quantitative and/or qualitative criteria that provide a simple and reliable means to measure achievement or reflect changes connected to the goal. | How the information on the indicator will be collected (can include who will collect it and how often). | External conditions necessary if the Goal is to contribute to the next level of intervention. |
| Outcomes The primary result(s) that an intervention seeks to achieve, most commonly in terms of the knowledge, attitudes or practices of the target group. | Outcome Indicators As above, connected to the stated outcome. | As above | External conditions not under the direct control of the intervention necessary if the outcome is to contribute to reaching intervention goal. |
| Outputs The tangible products, goods and services and other immediate results that lead to the achievement of outcomes. | Output Indicators As above, connected to the stated outputs. | As above | External factors not under the direct control of the intervention which could restrict the outputs leading to the outcome. |
| Activities The collection of tasks to be carried out in order to achieve the outputs. | Process Indicators As above, connected to the stated activities. | As above | External factors not under the direct control of the intervention which could restrict progress of activities. |

| EXAMPLE 1: WATER AND SANITATION PROJECT |
| --- |
| OBJECTIVES (What you want to achieve) | INDICATORS (How to measure change) | MEANS OF VERIFICATION (Where & how to get information) | ASSUMPTIONS (What else to be aware of) |
| Goal: Reduce death and illness related to Water and Sanitation related diseases in the targeted communities | G1 % (percentage) reduction in water and sanitation related diseases among target population G2 % of children under 36 months with diarrhoea in the last two weeks | Ministry of Health / WHO statistics Records from village clinics |  |
| Outcome 1 Improved access to and use of sustainable sources of safe water in target communities | 1a % of people in the target communities using minimum 25L of safe water per day 1b % of targeted households with access to an functional water source 1c % of water points managed by local WatSan committees 1d # hours spent by women in fetching water daily | 1a,b,d Household survey 1c Key informant interviews with WatSan committee members | Civil war / hostilities do not return Improved access to clinical health facilities |
| Outputs Community water points constructed or rehabilitated | 1.1a # (number) of water points constructed to national standard (140) 1.1ab% of water handpumps rehabilitated to national standard (35) | “Community Facility Inspection” field report | Low rainfall does not limit overall water supply. |
| Community management of water points is improved | 1.2a # of communities with a WatSan committee established 1.2b # of WatSan committees with technicians trained to perform basic maintenance on water points 1.2c % of WatSan committees collecting adequate charges to maintain the water points | 1.2a Household survey Key informant interviews with WatSan committee members | No major disputes or conflicts within the community |
| Outcome 2 Improved access to and use of sustainable sanitation facilities among targeted communities | 2a % of people in the target communities using latrines on a daily basis 2b % of targeted households with access to functional latrines meeting national standard 2c % of latrines managed by local WatSan committees | 2a,b Household survey 2c Key informant interviews with WatSan committee members | Civil war / hostilities do not return |
| Outputs Sanitation facilities constructed | 2.1a # of fully functioning household latrines constructed (3,500) | “Community Facility Inspection” field report | Flooding or other environmental problems do not affect sanitation facilities |
| Sanitation facility use is promoted | 2.2a # of demonstration toilets constructed (25) 2.2b # of awareness session on use of latrines (25) 2.2 c # of people reached by sanitation promotion activities (2000) | “Community Facility Inspection” field report |  |
| Community management of sanitation facilities is improved | See also indicator 1.2a 2.3a # of community WatSan committees with technicians trained to perform basic maintenance sanitation facilities 2.3b % of WatSan committees collecting adequate charges to maintain the sanitation systems | Key informant interviews with WatSan committee members | No major disputes or conflicts within the community |
| Outcome 3 Enhanced practice of safe hygiene and sanitation in the household | 3a % of households storing drinking water in separate, covered containers. 3b % of households storing food in sanitary, covered containers | Household survey | Civil war / hostilities do not return |
| Outputs 3.1 Household knowledge increased on safe hygiene & sanitation | 3.1 % of people (men/women) who can correctly identify at least 3 critical times when to wash hands. | Household survey | Cultural practices (unknown to project team) do not go against practices promoted |
| 3.2 Household training on safe hygiene and sanitation provided | 3.2a % of households trained in safe hygiene and sanitation practices including at least one female member. 3.2b # of trainings on safe hygiene and sanitation practices given | Training report. | People continue to have sufficient time to attend training |

| EXAMPLE 2: COMMUNITY & SCHOOL DISASTER MANAGEMENT (DM) PROJECT |
| --- |
| Objectives | Indicators | Means of verification | Assumptions |
| Goal: Reduce deaths and injuries related to disasters in the Eastern District. | G1: ratio of deaths caused by disaster to number of people exposed to a disaster in the target district (10:100,000 within 2 years) G2: % of injuries caused by disasters within population exposed to a disaster in the target district (5% within 2 years) | G1: Xland Government Disaster Management Agency statistics for the region (analysed by project manager, annually) G2: Sample survey by branch disaster management officers (reviewed 6 monthly by project manager) | No major unexpected epidemics, serious civil unrest or “mega-disaster” occur. |
| Community Disaster Management Capacity Building |
| Outcome 1: The capacity of communities to prepare for and respond to disasters is improved. | 1a: % of people in participating communities who practise 5 or more disaster preparedness measures identified in the community DM plan (80% in 2 years) 1b: % of targeted communities with identified response mechanisms in place (80% in 2 years) | 1a: Focus group discussions during CDMC meetings (monthly, by CDMC members & Red Cross volunteers). 1b: CDMC meetings/DM plans (collected & verified by project officer) | The political and security situation remains stable allowing community-level actions to be carried out. |
| Output 1.1: Community Disaster Management Plans are developed and tested by Community Disaster Management Committees (CDMCs). Output 1.2: Early warning systems to monitor disaster risks are established. Output 1.3: Communities’ awareness of measures to prepare for and respond to disasters is improved. | 1.1: # of participating communities that have a tested Disaster Management Plan (16 [out of 20] within 2 years) 1.2: % of communities with an early warning system in place (90% within 2 years) 1.3: % of people [of which 50% are female] in participating communities who can identify at least 5 preparedness and 5 response measures. (75% within 1 year) | 1.1: Copies of DM plans (collected by project manager) 1.2: Field officer’s report 1.3: Focus group discussions (every 3 months, by National Society volunteers & project staff) – cross-checked during annual disaster simulation (annually by CDMC members & National Society project officers) | The economy remains stable, and food shortages do not become acute. The security situation in the country does not prevent implementation of the DM plan. Local political leaders support implementation of the findings of the VCA. |
| Activities (for Output 1.1) Organize 10 community planning meetings. Engage volunteer peer facilitators. Develop/translate community DM awareness materials. | Inputs/resources 1.1.1: Space to hold meetings, trainers/peer facilitators, training materials 1.1.2: Per diems 1.1.3: Computers, printers, awareness-raising materials, translator | Costs & sources CHF 20,000 (appeal), CHF 2,000 (locally raised funds), volunteer time, donated space for meeting/training | People in the community have no new demands on their time preventing them from participating. |
| Activities for other outputs | Inputs & resources for other outputs | Costs & sources for other outputs |  |
| School-based Disaster Management Capacity Building |
| Outcome 2 The capacity of schools to prepare for and respond to disasters is improved | 1a: % of schools that have passed the annual disaster safety inspection from the Ministry of Disaster Management (80% within 2 years) 1b: % of participating schools that have successfully conducted 1 disaster simulation (60% within 1 year and 80% within 2 years) | 1a: Ministry of Disaster Management records 1b: Project reporting system through a simulation checklist | The political and security situation remains stable allowing school-level actions to be carried out. |
| Output 2.1 School Disaster Management plans are developed and tested at participating schools. Output 2.2: School Disaster Management Groups (DMGs) are formed in participating schools. Output 2.3: Disaster risk reduction lessons are included in the curriculum. | 1.1: # of participating schools that have a new DM Plan tested (20 [out of 25] within 2 years) 1.2: % of DMGs that have at least 2 teachers/staff, 2 parents, 2 students, and conduct regular monthly meetings (80% within 2 years) 1.3: % of students [of which 25% are female] in the targeted schools who have received disaster preparedness and disaster risk education | 1.1a: Copy of school DM plan (checked by project manager, every 6 months) 1.2a: DMU meeting minutes (checked by project manager, every 6 months) 1.3a: School classroom reports (project manager & volunteer, every 6 months) | Students are not taken out of school by their parents. The majority of teachers remain in their jobs for at least 1 year. |
| Activities (for output 2.1) Organize 10 school planning meetings. Train school teachers in facilitating DM planning. Develop/translate school-based DM awareness materials. | Input/ Resources 2.1.1: Space to hold meetings, trainers/peer facilitators, training materials 2.1.2: Classroom, training materials 2.1.3: Computers, printers, awareness raising materials, translator | Costs & sources CHF 10,000 (appeal), CHF 3,000 (locally raised funds), volunteer time, donated space for meeting/training | People in the community have no new demands on their time preventing them from participating |
| Activities for other outputs | Inputs & resources for other outputs | Costs & sources for other outputs |  |

# Footnotes

When there is more than one outcome in a project the outputs should be listed under each outcome – see the examples on the following pages.

Activities may often be included in separate document (e.g. activity schedule / GANTT chart) for practical purposes