**Field Assessment Information (15-25 March)**

A primary assessment was done by LRC team among the 1,048 households in 12 villages (Khokkong, Thaouan, Donmuang, Donbok, Pindong, Tamoryord, Hinlath, Hadoudomsay, Sompoy, Hadyao, Tangao and Hinsombat) under Samamsay district. The figure demonstrates the number of beneficiaries for shelter is about 321 households combine 10 villages (Thaouan, Donmuang, Donbok, Pindong, Tamoryord, hadoudomsay, Sompoy, Hadyao, Tangao and Hinsombat ). Hence, there are 2 types of latrine construction which are a new latrine and latrine repair, the assessment shows the needs of new latrine is 225 households and 183 households needed to be repaid. Currently the assessment team is summarising the data for livelihoods support. The data validation process is also ongoing to select the final beneficiaries.

The following steps were followed during the assessment:

|  |  |  |  |
| --- | --- | --- | --- |
|  | Activities | Outcome | Remarks |
| Step 01 | Join Meeting with LRC HQ and Chapter officials | The meeting allowed participants to understand the EA Recovery Plan of Action including budget and timeline | - LRC President presided the meeting  - IFRC, LRC HQ and Chapter officials were present |
| Step 02 | Meeting with the Attapeu Provincial Governor and other Officials | The Provincial Government has well informed about the recovery programme | - LRC President presided the meeting  - IFRC, LRC HQ and Chapter officials were present |
| Step 03 | Meeting with the Sanamsay District Governor and other officials | - The District Government has well informed about the recovery programme  - Identified the areas/villages where LRC will be implementing different activities | - IFRC, LRC HQ and Chapter officials were present |
| Step 04 | Meeting with the Head of Villages | -All the village heads have well informed about recovery activities  -Identified the current needs in the village | - IFRC, LRC HQ and Chapter officials were present |
| Step 05 | Assessment in the Field | -Identified the beneficiaries for each sector  -Identified the communities/villages for Health/WASH | IFRC, LRC staffs and volunteers including village leaders have participated in the assessment |
| Step 06 | Feedback Meeting with the District Authority | -Discussed the preliminary assessment report | LRC team was present |

Area of interventions:

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl # | Name of Village | Total HH | Shelter repair | HH Latrine | Livelihoods | WASH | Health | DRR |  |
| 01 | Kokkhong | 228 |  |  |  |  |  |  |  |
| 02 | Thaouan | 170 |  |  |  |  |  |  |  |
| 03 | DoneMouang | 228 |  |  |  |  |  |  |  |
| 04 | Done Bok | 171 |  |  |  |  |  |  |  |
| 05 | PinDong | 94 |  |  |  |  |  |  |  |
| 06 | Tamoyod | 98 |  |  |  |  |  |  |  |
| 07 | Hinlath | 168 |  |  |  |  |  |  |  |
| 08 | Had Oudomxay | 118 |  |  |  |  |  |  |  |
| 09 | Sompoy | 317 |  |  |  |  |  |  |  |
| 10 | Had Yao | 209 |  |  |  |  |  |  |  |
| 11 | Ta Nago | 69 |  |  |  |  |  |  |  |
| 12 | Hin Sombat | 66 |  |  |  |  |  |  |  |